## 1-Deployment Plan
Phase | Objective | Owner | Due Date | Tasks | Reference Materials | Est. Days to Complete
Set-up and Project Team Roll-out | Identify the LastPass Project Team |  |  | 1. Internal account manager(s): responsible for oversight and ongoing program management |  | 1
.. |  |  |  | 2. Internal security contacts: responsible for LastPass Policy configurations |  | 1
|  |  |  | 3. Internal System Administrators: responsible for the installation and configuration of directory sync |  | 1
|  |  |  | 4. Identify your Helpdesk Experts (maybe entire helpdesk) |  | 1
|  |  |  | 5. Schedule LastPass Introductory Demo for Project Team (See LP intro and Demo Links >>) | Video: LastPass Enterprise Demo (30 minutes) | 1
Video: LastPass Enterprise Admin Dashboard (1 min)
Video: LastPass Enterprise User Demo (14 minutes)
Explore Lastpass videos
Support: Get Started, Explore Features, Admin Tools
Link to register for weekly Admin and End User training Webinars
| Provision Project Team |  |  | 1. Provision accounts for all members of the LastPass Project Team | Support topic: How to Add Enterprise Users | 1
|  |  |  | 2. Then grant Admin rights to all members of the project team that require access | Support topic: View and Manage Enterprise User Settings
| Review Software Installation and Provisioning Options and Welcome email |  |  | 1. Review Software Installation Options and identify preferred method of installation on user devices | Support topic: Install LastPass Software Using the Admin Console | 1
Support topic: Download and Install LastPass
|  |  |  | 2. Determine if you will customize your Welcome email template or use Standard? --Let your CSM know if you customize it so your template can be approved. | Download and review Welcome to LastPass email template
|  |  |  | 3. Determine whether federatd login will be offered or seperate master password will be required for account registration. | Support topic: Federated Login Experience for LastPass Enterprise Users
Support topic: What are the limitations for federated (AD FS) LastPass Enterprise users?
Support topic: Set Up Federation Services (AD FS) for LastPass Enterprise
|  |  |  | 3. Review Automatic Provisioning and Directory integration options (LastPass AD connector, API, Windows, Microsoft, Azure, Okta, OneLogin) | Support topic: Use Directory Integrations for Automated Provisioning
Video: LastPass Enterprise Active Directory Connector Demo
| Explore Admin Console Available Features |  |  | Determine which features you would like to implement | Support topic: Overview of LastPass Enterprise solution | 1
|  |  |  | Single Sign-on (SSO) | Support topic: Access the LastPass SSO Admin Console
Support topic: What are Cloud Apps and how do I use them
Historical support topic (pre-July 2019): Set Up Single Sign-On for LastPass
|  |  |  | Explore MFA account trial | Support topic: How to trial LastPass MFA account
Review Advanced options
|  |  |  | Roles | Support topic: Manage LastPass Enterprise User Roles
|  |  |  | Push sites to users | Support topic: Push Sites to Users Vaults
|  |  |  | Advanced Enterprise options | Support topic: Advanced Enteprise Options
|  |  |  | >> Global Equivalent Domains | Support topic: Enterprise Admin Management of Global Equivalent Domains
|  |  |  | >> Global Never and Global Only URLs | Support topic: Enterprise Admin Management of Global Never and Global Only URLs
|  |  |  | >> Enterprise Admin Management of Master Passwords | Support topic: Enterprise Admin Management of Master Passwords
|  |  |  | >> Enabling Multifactor Authentication | Support topic: Enable Multifactor Authentication (Admins)
Support topic: Enterprise Admin Management of Multifactor Authentication Options
|  |  |  | >> Splunk Integration | Support topic: How do I integrate Splunk with my LastPass Enterprise account
|  |  |  | URL rules | Support topic: How do I manage my URL Rules as an Enterprise admin
Review Features
|  |  |  | Groups | Support topic: Add and Manage LastPass Enterprise Groups
|  |  |  | Shared Folders Feature | Support topic: About LastPass Enterprise Shared Folders
|  |  |  | Manage Shared Folders Admin | Support topic: View and Manage LastPass Enterprise Shared Folders (Admins)
|  |  |  | Manage Shared Folders User | Support topic: Manage LastPass Enterprise Shared Folders (Users)
|  |  |  | Linked Personal Accounts | Support topic: Link or Unlink Your Personal Account from LastPass Enterprise
|  |  |  | Form Fill | Support topic: Manage Your Form Fills
|  |  |  | Secured Notes | Support topic: Manage Your Secure Notes
|  |  |  | Secure Passwords | Support topic: Generate Secure Passwords
|  |  |  | Password Recovery options | Support topic: Recover Your Lost Master Password
| Review Policy Options-determine which ones to implement |  |  | 1. Consider your Local and Global Security Policies | Support topic: Local and Global Security Options | 1
|  |  |  | 2. Review the Enterprise Policy Options carefully (Default, Recommended, Consideration notes) See Tab 2 for Policy List and to take notes | Enterprise Policies
|  |  |  | 3. Review How to Add and Manage Policies from Admin Console | Support topic: Add and Manage Enterprise Policies
|  |  |  | 4. Schedule a Policy Review Meeting with your LastPass CSM to review and ask questions | [insert CSM OnceHub metting link here]
| Email Notifications |  |  | 1. Configure Email Notifications to monitor program and to automate emails to end users | Admin Console: Email Notifications | 1
Support topic: Manage Email Notifications for LastPass Enterprise
| Reports |  |  | 1. Review Admin Console Enterprise Reporting tool | Support topic: Generate Enterprise Reports | 1
| Pre-Load Users Vaults |  |  | 1. Audit company tools and sites used internally |  | 3
| - Shared Folders, Single Sign-on (SSO), Push sites |  |  | 2. Categorize sites: Shared or Individual
3. Set up Shared Folders, SSO, and Push Sites to Users (if applicable)
| Testing by the Project Team |  |  | 1. Test the top sites and applications utilized by your employees to ensure they are functioning seamlessly | Support topic: Add a New Site | 3
Support topic: How do I add a new password
Support topic: How do I manage my site passwords
Support topic: Use the Sharing Center
2. Enable and test any SAML apps that you intend to use in full roll-out (if applicable)
3. Test all policies for proper configuration
4. Test any Equivalent Domains, Whitelists or Blacklists that you have enabled to ensure proper set-up/mapping
| Communications/Internal Training |  |  | 1. Review Full Communication and Training Plans on Tabs 5 & 6 and agree on initiatives. | Communication tool: LastPass Admin Awareness toolkit | 4
2. Assign Communication Plan owner.
Small Test Group Rollout | Set-up Test Group (Superuser Pilot Group) |  |  | 1. Define Test Group participants. | Focus on creating a small testing group that includes people from multiple departments across your organization for a more accurate picture of user experience and to create department Super users that will be able to assist other users during the full roll-out. | 1
2. Inform Project Team of test group launch date and scope.
3. Define Project Milestones and Success Measurements for test group.
| Communications - Test Group |  |  | 1. Send email to all test group participants informing them of the upcoming roll out, the purpose of the program and corporate expectations. |  | 1
2. Highlight that they should expect a welcome email from LastPass in the next 24 hours.
| Test Group Launch |  |  | 1. Provision Test Group participants |  | 1
2. Conduct end user training
3. Customized training materials should steer the user to the helpdesk FAQs and helpdesk personnel with questions
| Communications - Company-wide Announcement |  |  | 1. Following Communication Plan (Tab 5), send communication to all employees informing them of the upcoming roll out, the purpose of the program, and corporate expectations |  | 1
2. Send out links for onboarding of users (Support Screencasts) and other materials for self-training
| Monitoring for Participation and Compliance |  |  | 1. Check the notifications report for usage statistics among test group |  | 14
2. Conduct outreach/training for anyone not currently using
| Pilot Group Wrap-Up - Measure Beta Results |  |  | 1. Survey test group on ease of implementation, training and satisfaction ratings | Return on Investment (ROI) Calculator | 2
2. Check Security Challenge History and other performance indicators in Admin Console
3. Capture total number of logins and calculate savings
4. Make changes to the implementation strategy based on survey learnings
Company-wide Rollout | Communications - Launch Announcement and Training |  |  | 1. Following Communication Plan, send email to entire company (or all participants) informing them of the start of the roll out, the purpose of the program,corporate expectations, and educational material (FAQs, links to training videos, information on getting support) | Communication tool: Secure password management made easy | 1
Communication tool: LastPass Admin Education toolkit
2. Highlight that they should expect a welcome email from LastPass in the next 48 hours
|  |  |  | 3. Schedule End User Training with CSM or Utilize weekly Live Trainings | Training tool: Register for Live End User Training
Training tool: Use the LastPass Self-Service Training Portal
Support topic: Get Started as a LastPass Enterprise User
Video: End User Training (16 min)
| Launch |  |  | 1. Provision accounts for every target user |  | 14
|  |  |  | 2. Implement full end user training and education program | Training tool: Download LastPass End User training presentation
Training tool: Download LastPass End User Training Script
3. Check the Admin console notifications report for usage statistics and for compliance
4. Survey users on satisfaction ratings and impact on productivity
| Review |  |  | 1. Conduct project end meeting to measure success on product delivery and adoption, agree on next steps, and pass on the project to the assigned CSM for ongoing support.

## 2-Policies
# | Category | Type | Policy | Considerations | Value | Applies To | Description | Federated Login?
1.01 | Login Rules |  | Restrict access by IP address |  |  |  | IP Address Restriction allows you to limit your users' access to their accounts to a certain set of IPs, such as only your office IP addresses. In the 'value' field, enter each IP address or partial IP address that you'd like to allow, separated by white space. For example: 71.126.154. 128.8. 120.0.0.1 would allow any address in 71.126.154.*, 128.8.*.* and 120.0.0.1 to login. Any matching IP address will allow entry. A matching DNS restriction or country restriction will also allow entry. We also support CIDR Notation for example: 61.12.56.0/24 would allow any address in 61.12.56.* to login.
1.02 | Login Rules |  | Restrict access by IP address (mobile excluded) |  |  |  | IP Address Restriction allows you to limit your users' access to their LastPass accounts to a certain set of IPs *except for mobile logins*, such as only your office IP addresses. In the 'value' field, enter each IP address or partial IP address that you'd like to allow, separated by white space. For example: 71.126.154. 128.8. 120.0.0.1 would allow any address in 71.126.154.*, 128.8.*.* and 120.0.0.1 to login. Any matching IP address will allow entry.
1.03 | Login Rules |  | Restrict access by reverse DNS |  |  |  | DNS Restriction allows you to restrict by domain name the IPs from which your users are permitted to login to LastPass. In the 'value' field, enter any permitted domain names, separated by white space. For example: comcast.com comcast.net verizon.net Would only allow users to login when the reverse DNS ended with comcast.com, comcast.net or verizon.net. Any matching IP address will allow entry. A matching IP restriction or country restriction will also allow entry.
1.04 | Login Rules |  | Restrict access by country |  |  |  | Country Restriction allows you to restrict the countries from which your users are permitted to login to LastPass. In the 'value' field, enter the two character permitted domain country abbreviation, separated by white space. For example: US CA Would only allow users to login when the country code for their IP is in the United States or Canada. Any matching country code will allow entry. A matching IP restriction or DNS restriction will also allow entry. For a list of country codes, see https://lastpass.com/listcountrycodes.php
1.05 | Login Rules | Default | Block TOR Access |  | Enabled | All | TOR Restriction allows you to restrict logins to LastPass accounts from The Onion Router (TOR) exit node IPs.
1.06 | Login Rules |  | Prohibit account recovery |  |  |  | Prohibit employees utilizing the 'account recovery' process to gain access to their account without the master password. Click the 'enabled' box to enable this policy. Caution: When this policy is enabled, account recovery will be impossible unless the 'Super Admin - Master Password Reset' policy is also enabled. | *Policy DOES NOT apply for Federated Login*
1.07 | Login Rules |  | Prohibit offline access |  |  |  | Prohibit your employees from logging in without a network connection. Click the 'enabled' box to enable this policy. This will mean that the user's data will no longer be stored locally on the device. We do not recommend this option as it means that in the unlikely case of an outage the data will be unavailable until connectivity is restored. | *Policy DOES NOT apply for Federated Login*
1.08 | Login Rules | Default | Prohibit 'Remember master password' |  | Enabled | All | By default (without this policy in place) the user has the option to 'remember password' upon login to LastPass. If this policy is added and disabled, then employees will be prohibited from allowing their LastPass browser extension to remember the master password. Uncheck the 'enabled' box to disallow. | *Policy DOES NOT apply for Federated Login*
1.09 | Login Rules |  | Prohibit account access on mobile devices |  |  |  | Disallow access from mobile phones and m.lastpass.com. If mobile access is attempted, the user will be presented with a notification that their employer does not allow account access from a mobile device. Click the 'enabled' box to enable this policy.
1.1 | Login Rules |  | Prohibit login from 'Denied' devices | When this policy is set Mobile devices are approved by the user in their own vault > Account settings > Mobile Devices |  |  | Restrict mobile logins to LastPass accounts to specific mobile devices. Devices must be specifically given access via: https://support.logmeininc.com/lastpass/help/manage-account-settings-lp010017#Mobile Click the 'enabled' box to enable this policy.
1.11 | Login Rules |  | Prohibit login from 'Denied' devices unless approved | When policy is set and user tries to log in from mobile they will get a notification saying the admin needs to approve the login. The admin would then approve them in Admin Console > Advanced Options > Trusted Mobile devices |  |  | Restrict mobile logins to LastPass accounts to specific mobile devices. Devices must be specifically given access by an admin in the Admin Console. Click the 'enabled' box to enable this policy.
1.12 | Login Rules |  | Prohibit login from jailbroken phones |  |  |  | Do not allow logins on jailbroken iOS and Android phones.
1.13 | Login Rules | Recommended | Restrict login attempts before lockout | Default is 5 |  |  | Set a custom number of failed login attempts before a user's account is locked, preventing further login attempts for a set period of time. **Only values between 3-8 are accepted.
1.14 | Login Rules | Recommended | Lockout period | Default is 15 minutes |  |  | Set a custom amount of time a user's account remains locked after they have failed to log in multiple times in a row. **Only values between 10-60 accepted.
1.15 | Login Rules |  | Disable email verification for new devices |  |  |  | By default, when a user tries accessing their LastPass account on a new device, two-step verification is required via the user's email address. The verification link must be successfully clicked to allow authentication on the new device. Enabling this policy will turn off this security requirement. Caution: Disabling email verification significantly reduces the security of users' LastPass accounts. We recommend against enabling this policy
2 | Logoff Overides | Recommended | Account logoff on browser close | If you want to override General Security Log Off Preferences set by the user. |  |  | By default (without this policy enabled) the employee is able to configure their automatic logoff preferences for their LastPass browser extensions. This policy allows you to override this setting. Once this policy is enabled, LastPass will log them off immediately after each session, so when they relaunch the web browser, they will be asked to enter their Master Password. Click the 'enabled' box to enable this policy.
2.01 | Logoff Overides |  | Account logoff on browser idle (extension) |  |  |  | By default (without this policy enabled) the employee is able to configure their automatic logoff preferences for their LastPass browser extensions. This policy allows you to override user's browser setting. In the 'value' field, enter the number of minutes (0-9999) of idle status that you would like to allow on the user's device prior to automatic logoff from the LastPass extensions.
2.02 | Logoff Overides |  | Account logoff on computer lock |  |  |  | This policy allows you to override user's browser setting to logoff the user on computer lock. **LastPass for Applications must be running in order for this policy to work.
2.03 | Logoff Overides |  | Account logoff on screensaver |  |  |  | This policy allows you to override user's browser setting to logoff the user on computer lock. **LastPass for Applications must be running in order for this policy to work.
2.04 | Logoff Overides |  | Account logoff on shutdown/logoff |  |  |  | This policy allows you to override user's browser setting to logoff the user on computer lock. **LastPass for Applications must be running in order for this policy to work.
2.05 | Logoff Overides |  | End existing sessions on login |  |  |  | If you leave your browser session open and polling is enabled, you'll be logged out of the other session. If your browser session is closed but you leave yourself logged into LastPass, this can also be helpful: (e.g., your browser is closed at work, and you login from home with this setting enabled, you will be required to login the next time you open up your browser at work.)
2.06 | Logoff Overides |  | Account logoff on browser idle (website) | We recommend 30 minutes - typically, users don't use the online vault unless they are on a shared machine without the extension installed, and you want to ensure they are logged out if they walk away. |  |  | By defaut (without this policy enabled) the employee is able to configure their automatic logoff preferences for the LastPass website. This policy allows you to override this setting. In the 'value' field, enter the number of minutes (5-20160) of idle status that you would like to allow on the user's device prior to automatic logoff from the LastPass website.
3.01 | Master Password Strength | Recommended | Length of master password | We typically recommend following your established AD password policy for length and complexity. |  |  | Require employees to have a minimum number of characters in their master password. In the 'value' field, enter the number of desired characters. Once enabled, employees will be prompted upon creating or editing the master password if the new password fails to meet the specified criteria. Values must be greater than or equal to 8. If you wish to have a different limit if multifactor is used, you can specify 2 numbers, separated by a comma (for example, 12,9). | *Policy DOES NOT apply for Federated Login*
3.02 | Master Password Strength |  | Minimum digits in master password |  |  |  | Require employees to have a minimum number of numeric digits in their master password. In the 'value' field, enter the number of desired numeric digits. Once enabled, employees will be prompted upon creating or editing their master password if the new password fails to meet the specified criteria. | *Policy DOES NOT apply for Federated Login*
3.03 | Master Password Strength |  | Minimum lowercase in master password |  |  |  | Require employees to have a minimum number of lowercase characters in their master password. In the 'value' field, enter the number of desired numeric digits. Once enabled, employees will be prompted upon creating or editing the master password if the new password fails to meet the criteria set in this policy. | *Policy DOES NOT apply for Federated Login*
3.04 | Master Password Strength |  | Minimum uppercase in master password |  |  |  | Require employees to have a minimum number of uppercase characters in their master password. In the 'value' field, enter the number of desired uppercase characters. Once enabled, employees will be prompted upon creating or editing their master password if the new password fails to meet the specified criteria. | *Policy DOES NOT apply for Federated Login*
3.05 | Master Password Strength |  | Minimum special characters in master password |  |  |  | Require employees to have a minimum number of special characters (e.g. !@,^) in their master password. In the 'value' field, enter the number of desired special characters. Once enabled, employees will be prompted upon creating or editing the master password if the new password fails to meet the specified criteria. | *Policy DOES NOT apply for Federated Login*
3.06 | Master Password Strength | Recommended | Minimum character sets in master password | We typically recommend following your established AD password policy for length and complexity. |  |  | Require employees to have a minimum number of different character sets in their master password. The 'characters sets' are (1) uppercase, (2) lowercase, (3) numeric, and (4) special (e.g. !@#$,^ etc). The default is one. In the 'value' field, enter a value between 2 and 4 to increase the minimum number of character sets that must be included in the master password. For example, if you enter 3 then the user must include at least 3 different types of characters from the list (lowercase, uppercase, and numeric; uppercase, numeric, and special; uppercase, lowercase, and special; etc). Once enabled, users will be prompted upon creating or editing their master password if the new password fails to meet the specified criteria. | *Policy DOES NOT apply for Federated Login*
4.01 | Site Password Strength | Recommended | Length of site passwords |  |  |  | Require employees to have a minimum number of characters in their password for a specific site. In the 'value' field, enter the domain(s) (separated by commas if there are multiple), followed by an equal sign, followed by the number of desired characters. You can separate multiple entries with white space. For example: twitter.com=20 google.com,gmail.com=15 Once enabled, the password generator tool will not support the creation of passwords shorter than the length stipulated. Note: we can control the password generator only, and not the value that is ultimately submitted on the page.
5.01 | Limit Features |  | Prohibit export | We recommend enabling this policy as a best practice, if a user has a legitimate need to export it can be temporarily disabled to allow them to do so. |  |  | Disallow your users from exporting their account data. Click the 'enabled' box to enable this policy. When enabling this policy, it is also recommended that you use the installer switch -dexp to hide this function in the client software. Please note that based on the client-side restriction nature of this policy, this is not a full prevention of exporting; the policy makes it more difficult for users to access the export from the UI.
5.02 | Limit Features |  | Prohibit import |  |  |  | Disallow your users from importing data from other sources. Click the 'enabled' box to enable this policy. When enabling this policy, it is also recommended that you use the installer switch -dimp to hide this function in the client software.
5.03 | Limit Features |  | Prohibit sharing |  |  |  | Disallow your users from sharing their sites, notes, and other data with other users. Click the 'enabled' box to enable this policy. When enabling this policy, it is also recommended that you use the installer switch -dsha to hide this function in the client software.
5.04 | Limit Features |  | Prohibit shared folders outside enterprise | If there is no use case for external password sharing, we recommend turning on this policy. |  |  | Disallow your users from assigning shared folders to individuals outside of your enterprise.
5.05 | Limit Features | Recommended | Prohibit sharing except shared folders | This policy removes the option to share an individual item, so that shared items must be shared in a folder. This gives more auditability and accountability to sharing in your organization and ultimately control to IT over shared credentials if needed. |  |  | Disallow your users from sharing their sites, notes, and other data with other users except via shared folders (which is limited to intra-company). Click the 'enabled' box to enable this policy.
5.06 | Limit Features |  | Restrict sharing by domain |  |  |  | Allow sharing to only users in the specified domains. In the 'value' field, enter the permitted domains. Multiple domains can be separated by commas, e.g., aaa.com,bbb.com, etc.
5.07 | Limit Features |  | Prohibit master password reversion |  |  |  | Disallow reverting master password changes. | *Policy DOES NOT apply for Federated Login*
5.08 | Limit Features |  | Disable Identities | Manage Identities is an older feature (accessed from your Vault > More options) used to create profiles, for example to manage Work and Home related sites. This feature is no longer a focus since Linking Personal accounts was introduced. |  |  | Disable the Identities feature from showing up on the website and in the browser extensions.
5.09 | Limit Features |  | Disable Secure Notes |  |  |  | Disallow your users from using the Secure Notes feature of LastPass, if they have existing notes you will want to allow users to migrate them first as once set they will not be able to retrieve them. This policy only removes creation of new secure notes from the online vault. To remove secure notes from the plugins, please see the '--disablenotes' optional argument of the LastPass Universal Installer, which hides the secure notes feature for the Firefox and Internet Explorer browser plugins.
5.1 | Limit Features |  | Disable fingerprint reader authentication |  |  |  | Disallow your users from using Fingerprint Reader Authentication.
5.11 | Limit Features |  | Prohibit bookmarklets | Bookmarklet is a special type of 'Favorite' or 'Bookmark' that executes code on the page you're viewing. This is an older feature (accessed from your Vault > More options) that isn't frequently used today. |  |  | Disallow your users from installing Bookmarklets.
5.12 | Limit Features |  | Prohibit master password hint |  |  |  | Prevent storing of master password hint. | *Policy DOES NOT apply for Federated Login*
5.13 | Limit Features |  | Hide Cloud Apps from users |  |  |  | If you are not using LastPass SSO, prevent end users from accessing LastPass SSO features by removing the Cloud Apps menu item from their vault.
5.14 | Limit Features |  | Disable Autofill |  |  |  | Disable Autofill allows you to disable the autofill of passwords on desktop applications including Chrome, Firefox, Safari and Edge. This will not impact the mobile autofill experience. When the policy is enabled, the Automatically Fill Login Information option will be disabled from the enterprise user.
6.01 | Master Password Rules |  | Require master password on site login |  |  |  | Require re-entry of the master password when logging into sites. Once this policy is enabled, LastPass will prompt the user for their master password at every site login. This results in no autofill behavior, all website logins are manual (the user must click the login button on the site). Click the 'enabled' box to enable this policy.
6.02 | Master Password Rules |  | Require master password on copy/view |  |  |  | Require re-entry of the master password when copying or viewing passwords. Once this policy is enabled, LastPass will prompt the user for their master passwords at every attempt to copy or view a password. Click the 'enabled' box to enable this policy
6.03 | Master Password Rules | Recommended | Require master password change | We typically recommend 180 or 365 days when multi-factor authentication is enforced. |  |  | Require employees to change their master password after a specified number of days. In the 'value' field, enter the number of days between password resets. Once enabled, employees will be prompted to change their passwords after the specified time-frame. This is recommended to be set at 90 days if you do not require multifactor usage, and 365 days if you require multifactor. If you wish to have a different limit if multifactor is used, you can specify 2 numbers, separated by a comma (for example, 90,365). | *Policy DOES NOT apply for Federated Login*
6.04 | Master Password Rules |  | Prohibit master password reuse for sites |  |  |  | Require employees to change their master password after detecting that it has been used on another website. If an employee types their master password on another website, they will be logged off, and next time they login, they will be prompted to change their master password. | *Policy DOES NOT apply for Federated Login*
6.05 | Master Password Rules | Default | Prohibit reuse of old master passwords | We recommended increasing the value to at least 5. Ideally, you want users to always use a new one, not recycle a few. | 1 | All | Disallow reuse of master passwords on master password changes. Enter the number of historical passwords to check against in the box below. | *Policy DOES NOT apply for Federated Login*
7.01 | Multifactor |  | Prohibit multifactor disable via email |  |  |  | Prevent the user's ability to disable multifactor authentication via email.If this policy is set, the ONLY way to disable second factor is through the enterprise console by an administrator. | *Policy DOES NOT apply for Federated Login*
7.02 | Multifactor |  | Require use of LastPass Authenticator |  |  |  | Require use of LastPass Authenticator as a second factor of authentication when logging into LastPass. Click the 'enabled' box to enable this policy. LastPass Authenticator must be configured by the user. | *Policy DOES NOT apply for Federated Login*
| Multifactor |  | Require use of LastPass MFA
7.03 | Multifactor |  | Require use of YubiKey |  |  |  | Require use of a YubiKey as a second factor of authentication when logging into LastPass. Click the 'enabled' box to enable this policy. | *Policy DOES NOT apply for Federated Login*
7.04 | Multifactor |  | Require LastPass Sesame |  |  |  | Require use of LastPass Sesame as a second factor of authentication when logging into LastPass. Click the 'enabled' box to enable this policy. Sesame must be configured by the user as described here: https://helpdesk.lastpass.com/security-options/sesame-multifactor-authentication-with-a-usb-thumb-drive/. | *Policy DOES NOT apply for Federated Login*
7.05 | Multifactor |  | Require use of Google Authenticator |  |  |  | Require use of Google Authenticator as a second factor of authentication when logging into LastPass. Click the 'enabled' box to enable this policy. Google Authenticator must be configured by the user as described here: https://helpdesk.lastpass.com/security-options/google-authenticator/. | *Policy DOES NOT apply for Federated Login*
| Multifactor |  | Require use of Microsoft Authenticator
7.07 | Multifactor |  | Require use of Toopher |  |  |  | Require use of Toopher as a second factor of authentication when logging into LastPass. Click the 'enabled' box to enable this policy. Toopher must be configured by the user. | *Policy DOES NOT apply for Federated Login*
7.08 | Multifactor |  | Require use of Duo Security |  |  |  | Require use of Duo Security as a second factor of authentication when logging into LastPass. You must enter your integration key, secret key, and API hostname in the boxes below. Duo Security must be configured by the user. To require Duo Security x days after the user account is created, enter a number in the value field below. | *Policy DOES NOT apply for Federated Login*
7.1 | Multifactor |  | Require use of Transakt |  |  |  | Require use of Transakt as a second factor of authentication when logging into LastPass. Click the 'enabled' box to enable this policy. Transakt must be configured by the user. | *Policy DOES NOT apply for Federated Login*
7.11 | Multifactor |  | Require use of Salesforce Authenticator |  |  |  | Require use of Salesforce Authenticator as a second factor of authentication when logging into LastPass. Click the 'enabled' box to enable this policy. Toopher must be configured by the user. | *Policy DOES NOT apply for Federated Login*
7.14 | Multifactor | Recommended | Require use of any MFA option | This policy can be turned on after rollout but we recommend testing prior to rollout. |  |  | Require use of any multifactor option as a second factor of authentication when logging into LastPass. Click the 'enabled' box to enable this policy. YubiKey, LastPass Sesame, Google Authenticator, Toopher, Duo Security, SecureAuth, Transakt, Salesforce#, RSA SecurID, and Symantec VIP are the currently available options. | *Policy DOES NOT apply for Federated Login*
7.15 | Multifactor | Recommended | Require any MFA option after grace period |  |  |  | Require use of any multifactor option as a second factor of authentication when logging into LastPass after specified number of days in the value field. YubiKey, LastPass Sesame, Google Authenticator, Toopher, Duo Security, SecureAuth, Transakt, Salesforce#, RSA SecurID, and Symantec VIP are the currently available options. | *Policy DOES NOT apply for Federated Login*
7.16 | Multifactor |  | Allow users to skip MFA at trusted locations |  |  |  | Restrict computers that can be trusted by IP address (learn more about 'trusted computers' here: https://helpdesk.lastpass.com/account-settings/trusted-computers/. You can enable this policy to allow users to skip second factor authentication from trusted locations (such as the office) but still require it from remote locations. In the 'value' field, enter each IP address or partial IP address that you would like to allow separated by white space. For example: 71.126.154. 128.8. 120.0.0.1 would allow any address in 71.126.154.*, 128.8.*.* and 120.0.0.1 to be trusted. If you would like to disable trust altogether, enter 'none' in the input box. Disabling trust is not retroactive. Computers that were been previously trusted will still be trusted after enabling this policy. | *Policy DOES NOT apply for Federated Login*
7.17 | Multifactor |  | Prohibit offline access for TOTP MFA |  |  |  | Prevent offline access when using a TOTP-based multifactor option. The local cache can be accessed without a second factor, this policy will prevent that from occurring. | *Policy DOES NOT apply for Federated Login*
7.18 | Multifactor |  | Set code validity interval for Google Authenticator |  |  |  | Due to issues with clock drift on users' mobile devices, LastPass considers a Google Authenticator code valid up to 4 minutes in the past, and 4 minutes in the future. If a number between 0 and 5 is entered here, LastPass will use that number of minutes instead. | *Policy DOES NOT apply for Federated Login*
7.19 | Multifactor |  | Prohibit multiple YubiKeys |  |  |  | Prevent the user's ability to setup more than 1 YubiKey for their account. By default, LastPass allows a user to use up to 5 different YubiKeys. | *Policy DOES NOT apply for Federated Login*
7.2 | Multifactor |  | Use local-part of email as Duo Security username |  |  |  | By default, the user's full email address is used as their Duo Security username. Enabling this policy will cause only the username portion of the email address to be used. For example, if the user's email address is drew@lastpass.com and this policy is enabled, their Duo Security username would be drew. | *Policy DOES NOT apply for Federated Login*
7.21 | Multifactor |  | Require MFA for admin console |  |  |  | If this policy is in place, users accessing the enterprise console will be required to re-authenticate via multifactor after not using it for X minutes, where X is the number specified in this policy. | *Policy DOES NOT apply for Federated Login*
7.22 | Multifactor |  | Require action for out-of-band MFA |  |  |  | If this policy is in place, users using a multifactor option with out-of-band capability (currently Toopher, Duo Security, and Transakt) will not receive an automatic push notification. They will instead have to click or tap within the UI if they would like one. | *Policy DOES NOT apply for Federated Login*
7.23 | Multifactor |  | Use Duo Web SDK when possible |  |  |  | If this policy is in place, the Duo Web SDK will be used in lieu of the LastPass Duo Security GUI where possible. Please note that this will remove certain LastPass-specific features, such as automatic push notification. | *Policy DOES NOT apply for Federated Login*
7.24 | Multifactor | Default | Apply parent account MFA policy | If you do not want your corporate multi-factor authentication to "impose" upon an employee's personal LastPass account, we recommend disabling this default policy. |  |  | If this policy is in place, and a user's linked personal account doesn't have a multifactor authentication option enabled, the parent account's multifactor authentication option will be used instead. | *Policy DOES NOT apply for Federated Login*
7.25 | Multifactor |  | Skip MFA at trusted locations |  |  |  | If a login is attempted from the IPs supplied, users will not be prompted for their multifactor. In the 'value' field, enter each IP address or partial IP address that you'd like to allow, separated by white space. For example: 71.126.154. 128.8. 120.0.0.1 would allow any address in 71.126.154.*, 128.8.*.* and 120.0.0.1 to login without multifactor. We also support CIDR Notation for example: 61.12.56.0/24 would allow any address in 61.12.56.* to login. | *Policy DOES NOT apply for Federated Login*
8.01 | Administration |  | Don't send welcome email |  |  |  | Prevents sending a welcome email to new users (only works for automatic provisioning). Click the 'enabled' box to enable this policy.
8.02 | Administration |  | Don't send email upon account change |  |  |  | Prevents sending an account change status email to users when their master password or email has been changed. Click the 'enabled' box to enable this policy.
8.03 | Administration |  | Don't send email upon master password reset |  |  |  | Prevents sending an account change status email to users when the 'Super Admin - Master Password Reset' policy is used to reset the user's master password. Click the 'enabled' box to enable this policy.
8.04 | Administration |  | Prevent upgrade prompts on Internet Explorer |  |  |  | If enabled, this policy will prevent the LastPass IE plugin from automatically upgrading. It will also prevent users from seeing prompts when IE upgrades are available. Click the 'enabled' box to enable this policy.
8.05 | Administration | Default | Notify admins upon user lockout |  | Enabled | All | Sends an automated email to the specified email addresses when an account is temporarily locked because of too many failed login attempt. In the 'value' field, enter the desired email address(es). Multiple email addresses should be separated by commas. | *Policy DOES NOT apply for Federated Login*
8.06 | Administration |  | Notify admins upon added/removed user |  |  |  | Sends an automated email to the specified email addresses when a user account is added or removed from your Enterprise account. This is particularly useful when using automatic provisioning or our Active Directory client. In the 'value' field, enter the desired email address(es). Multiple email addresses should be separated by commas.
8.07 | Administration | Recommended | Permit super admins to access shared folders | This policy requires set-up; we always recommend enabling it. |  |  | All shared folders created in your enterprise will be invisibly shared with the specified username(s). The username(s) must be of an admin account in your enterprise. Click on 'Show List' to add the desired users as Super Admins. If you wish to disable the ability to add or change this policy by your admins, please contact LastPass. For shared folders that existed prior to setting this policy, they will be assigned the next time a user with 'Can Administer' access to that folder logs back into LastPass.
8.08 | Administration | Recommended | Permit super admins to reset master passwords | This policy requires set-up; we always recommend enabling it. Understand how this policy works review the following documentation: https://support.logmeininc.com/lastpass/help/reset-a-users-master-password-super-admin-lp010038 |  |  | Permits the re-set of a user's master password by the specified 'Super Admin'. All specified 'Super Admin' accounts must first be added as Administrators. All accounts created in your Enterprise will have their encryption key securely shared with the username specified below. Click on the 'Show List' link in the policy to add the desired super admins. This will allow the admin to recover the user's account by resetting the master password. The user must log into the plugin once after joining the enterprise in order to capture this data. All eligible master passwords can be reset by the Super Admin from the Users tab of the Admin Console: https://lastpass.com/enterprise_users.php. It is recommended that you protect this account with second factor authentication since it is so powerful. It is also possible, but not recommended, to specify multiple recovery admins by entering usernames in this field, separated by commas, spaces or semicolons. If you wish to disable the ability to add or change this policy by your admins, please contact LastPass.
8.09 | Administration |  | Grant limited access to admin console |  |  |  | Grant restricted Admin Console access to a User. In the Notes field of the policy, enter one of the following values to set the level of access. 1 - Only allows the Reset Master Password function for users, but not full admins. 2 - Disable Multifactor Authentication for users + (1) 3 - Management of the Users page + (1 and 2) 4 - Management of the Users and Groups pages + (1, 2 and 3) Only values between 1-4 are accepted. Notes: *Enabling password resets REQUIRES that you add the user to the Super Admin Master Password Reset policy after adding the user to this policy. *Adding a user to this policy prevents them from being added to custom Roles. *After adding a user to this policy, they will show as an Administrator on the Users page.
8.1 | Administration |  | Notify admins upon event |  |  |  | Send an email notification for specific events of interest, for the selected user or users, or groups. The value of this policy should be the event to send email about. Be careful about using this policy, as you may easily be swamped by emails. Users must be explicitly added to this policy. Currently supported values: 'login' - when user successfully logs into their LastPass account 'failedlogin' - when user attempts but fails to log into their LastPass account successfully. Multiple events may be specified, separated by commas or spaces. It is also permitted to specify the same policy multiple times. By default, the email notifications are sent to the selected user. However, you may optionally specify an alternate email address to send notifications to, distinct from the active user. To do so, specify the email address of the user account to send notifications for, followed by an equals '=' character, and then the email address that will receive the notifications. Example: failedlogin=elmer@mydomain.com
8.11 | Administration | Default | Pre-create sharing key |  | Enabled | All | When creating users automatically server-side (using batch provisioning, the LastPass Active Directory Sync Client, or the LastPass Provisioning API), this policy pre-creates their sharing key as well. Without this policy, users will not receive a sharing key until they login via the browser extension, and you will not be able to share items or folders with them. With this policy, you will be able to do so immediately. Please note that the sharing key will be created server-side, as opposed to being created client-side when created during user login. It is immediately encrypted using the user's temporary password, and is never stored in plaintext.
8.12 | Administration | Recommended | Notify admins upon account recovery |  |  |  | Sends an automated email to the specified email addresses when the 'account recovery' option is utilized by any employee. In the 'value' field, enter: The number '1' if you would like the email sent when account recovery is requested by an end user. The number '2' if you would like the email sent when account recovery is successfully completed and the user re-sets his/her master password. The numbers '1,2' if you would like both. In every case, these indications must be followed with the desired email address(es). Multiple email addresses should be separated by commas. Here is an example of a possible entry: '1,2,admin@acme.com,admin2@acme.com' | *Policy DOES NOT apply for Federated Login*
8.14 | Administration |  | Prevent user status emails to shared folder admins | There are a few things to consider with this policy. Because the email notifications may go through before an employee termination announcement is made, it could create awkward situations. However, it is best practice to change shared passwords when someone leaves the organization, and this reminds shared folder admins to take action at that time. |  |  | Disable automated emails to shared folder admins regarding a user's change in account status.)
8.15 | Administration |  | Restrict domain for LastPass username | This policy prevents a user from changing their Enterprise username (email address) to a Gmail account or other non-AD username. |  |  | When enabled, this policy will restrict the usernames of your users to approved domains only. No accounts can be created or updated using a username that is outside of the approved domains. Enter the allowed domains in the box below. Separate multiple domains with commas. For example: lastpass.com,xmarks.com
8.16 | Administration |  | Prohibit account email change |  |  |  | Disallow your users from changing their email address.
8.17 | Administration |  | Disable PasswordPing checks |  |  |  | Desc: The PasswordPing checks are disabled by enabling this policy at the following services: -Daily checks for LastPass account emails -Security Challenge reports -Email notifications (See more details https://blog.lastpass.com/2017/07/keeping-you-safe-in-a-world-full-of-breaches.html/)
9.01 | Reporting |  | Log username in reporting | We recommend enabling for more complete auditing logs. |  |  | By activating this policy, you allow LastPass to store username data unencrypted and to provide that data to you in reports. Important: LastPass never stores username data unencrypted unless you activate this policy. Logged in users must log in again for this policy to take effect. EXAMPLE If a user logs into a site that has username 'jackhandy' with url https://abc.com/, then by default we would display 'abc.com', but with this policy enabled we would display 'abc.com (jackhandy)'.
9.02 | Reporting |  | Log full URL in reporting | We recommend enabling for more complete auditing logs. |  |  | Show full URL (server + path, but no HTTP parameters) in reports rather than just the domain name of the site. This is often useful to distinguish which service is being accessed if many different resources are located on the same internal server. After changing this policy, your users must re-login into LastPass devices in order for it to take effect. EXAMPLE If a user logs into https://def.abc.com/login.php?a=1, then by default we would display 'abc.com', but with this policy enabled we would display 'def.abc.com/login.php'.
9.03 | Reporting |  | Log item name in reporting | We recommend enabling for more complete auditing logs. |  |  | Show name of site/note in reports. The name data (which is typically never sent to LastPass in unencrypted format) is sent by the client when reporting a login event and is shown in the admin reports. After changing this policy, your users must re-login into LastPass devices in order for it to take effect. EXAMPLE If a user logs into a site named ABC with url https://abc.com/, then by default we would display 'abc.com', but with this policy enabled we would display 'abc.com (ABC)'.
9.04 | Reporting |  | Notify admins upon creation of sharing key |  |  |  | Sends a notification to the specified email addresses when a user has created their sharing key. A user's sharing key is automatically created the first time they login to their account using a LastPass plugin, or can also be done manually via the LastPass website settings page. Items can be shared with a user only after their sharing key has been created.
10.01 | Mobile | Recommended | Require PIN |  |  |  | Require use of a PIN code when switching to the application.
10.02 | Mobile |  | Force logoff from background |  |  |  | Logoff after the app is in the background for the specified number of minutes.
10.03 | Mobile | Default | Log mobile activity |  | Enabled | All | Log password access and site filling so it is visible in reporting.
10.04 | Mobile |  | Prohibit 'Remember master password' on mobile | Remembering the password weakens the security for that user, we recommend enabling this policy as a best practice. |  |  | If set, the app is unable to remember the user's master password.
10.05 | Mobile |  | Override mobile lock option |  |  |  | Note: By default, users have the ability to configure their mobile lock preferences for the LastPass mobile apps. When this policy is turned on, you can specify when the user will be prompted to log in again or re-enter their PIN to unlock the app. To enable: Enter the required number (0 - 'Immediately', 1 - '1 minute', 2 - '3 minutes', 3 - '5 minutes', 4 - '15 minutes', 5 - '1 hour', 6 - '8 hours', 7 - '24 hours', 8 - 'Never') after a user navigates away from the LastPass mobile app and returns before they are prompted to login again with their master password or enter their PIN. Note: This policy is only available for the latest version of LastPass available in the app store (LastPass for iOS 4.1.8 or higher, and LastPass for Android 4.2.290 or higher).
11.01 | Linked Personal Account |  | Prohibit linked personal account |  |  |  | Disallow linking of personal account into your enterprise account.
11.02 | Linked Personal Account |  | Prohibit update of personal account info |  |  |  | Disallow adding/updating/deleting of personal account data when it is linked through your enterprise account.
11.03 | Linked Personal Account |  | Set default account for new sites |  |  |  | If this policy is in place, and a user has a linked personal account, sites will be saved to the personal account by default, unless the new site's URL matches a domain specified in the 'value' field below. Multiple domains can be separated by commas, e.g., aaa.com,bbb.com, etc.
11.04 | Linked Personal Account |  | Save personal sites to personal vault |  | Enabled | All | Linking a personal LastPass vault to the work vault allows a user to conveniently access both their personal and work credentials at the same time. Once linked, the user logs in to their work account to access both vaults. When this policy is enabled, LastPass detects the username for every new site. If the username matches the master username for the Personal Linked Account (such as @gmail.com), the site will be saved directly to the personal vault by default. If any other username is used for the site (such as @work.com or any non-email username), the site will be saved directly to the work vault by default. The user can override the LastPass personal account selection if needed. Note: A personal LastPass vault must be linked to the user’s work vault in order to auto-sort. Otherwise, all logins will save to the work vault by default. We recommend enabling the “Recommend or Require Linked Personal Account” policy in order to help automate this function for users.
11.05 | Linked Personal Account |  | Recommend or require linked personal account | We recommend setting this policy at 2 (a "recommended policy") to give users the option to set up the personal Linked Account while creating their Enterprise account. |  |  | When enabled, this policy will force each user to create a personal account that will be linked automatically to his/her Enterprise account. Existing personal account holders will be required to link their personal account. New users will enter their personal email address which will serve as the username for the account, while the master password will be the same for both accounts. Enter a 1 to make this policy mandatory. It will continue to pop on every login until setup. Enter a 2 to allow the user to opt-out if desired.
12.01 | Security Audit | Default | Show master password strength |  | Enabled | All | Collect and show master password strength for each employee. Data will be collected after next login. | *Policy DOES NOT apply for Federated Login*
12.02 | Security Audit | Recommended | Check for compromised user accounts |  |  |  | When performing a background security scan, check each username against a database of known third party security breaches to determine if accounts registered with that username may have been compromised. If the username is found to be associated with a login that is potentially at risk, an email will be sent to the user identifying the compromised website and recommending preventative measures.
12.03 | Security Audit |  | Password expiration notification |  |  |  | Report on password expiration status for each employee. This policy requires a list of domains to monitor and the expiration length per domain. An asterisk indicates all domains should be impacted. Include email addresses in the policy to have a report on all expired accounts emailed to an admin. Append A : and a number to have the admin alert email go out X days after the domain expiration. If no expiration time period is specified, 90 days is assumed. ie: domain.com:83, domain2.net:173, *:53, admin@domain.com:7 This would result in users being notified for passwords 53 days old for all domains, 83 days old for domain.com, 173 days old for domain2.net and admin@domain.com being alerted after the users have gotten 7 days of notifications.
12.04 | Security Audit | Default | Show security challenge score |  | Enabled | All | Run the security challenge automatically for each user after they login (in the background) and report the results. Scores can then be viewed in the User's Enterprise Console page.
13.01 | Limit Features |  | Disable AutoFill |  |  |  | Disable Autofill allows you to disable the autofill of passwords on desktop applications including Chrome, Firefox, Safari and Edge. This will not impact the mobile autofill experience. When the policy is enabled, the Automatically Fill Login Information option will be disabled from the enterprise user.

## 3-Email Notifications
Notification Name | Description
Invitation not accepted | Users who have not accepted an invitation to join your LastPass enterprise account within X hours of being invited. If manually invited, users need to click on the email invitation link to associate their LastPass account to your company's LastPass enterprise account.
Account not activated | Users who have not activated their LastPass enterprise account within X hours of being invited.
No sharing key | Users who do not have a sharing key. Users must login once using a LastPass plugin to generate a sharing key before you can share items with them.
Inactive | Users who have not logged in for more than X days.
Number of sites | Users who have less than X sites in their vault.
No Linked Account | Users who have not associated a personal LastPass account with their Enterprise account.
Weak master password | Users who have a master password strength of less than X percent.
Reused master password | Users who entered their master password on another site in the last X days and have since not changed their master password.
Weak security challenge | Users who have a security challenge score of less than X percent.
Weak passwords | Users who have more than X sites that have weak passwords.
Average password strength | Users whose average password strength is less than X percent.
Duplicate passwords | Users who have more than X duplicate passwords.
Duplicate password sites | Users who have more than X sites with duplicate passwords.
Blank passwords | Users who have more than X sites with blank passwords.
Low number of entries | Users who have less than X sites, secure notes, and Fill Form profiles in their vault.
Low number of secure notes | Users who have less than X secure notes in their vault.
Low number of Fill Forms profiles | Users who have less than X Fill Form profiles in their vault.

## 4-Adoption Best Practices
Action Item | Description | Owner | Dates | Status | Notes
Top Adoption Drivers
Assign an Executive Sponsor. | We recommend selecting a C or V level Executive to champion LastPass internally and receive regular reports of progress on the rollout. | Client
Make LastPass mandatory. | Consider creating a company policy that all employees are mandated to use LastPass. Deploy user training portal to track employee progress. | Client
Integrate with your user directory. | By integrating with your existing directory, every employee can be automatically onboarded to LastPass when they join the company, as well as off-boarded when they leave. You'll simplify day-to-day management for admins while spreading usage in the organization. | All
Hardwire LastPass. | Consider pre-loading user vaults for new hires with passwords they need to do their work. When they see that the vault is set up for them and LastPass starts filling their passwords automatically, they’ll instantly see the value of the service. | Client
Formalize a communication strategy. | Develop a plan for raising awareness of LastPass and training employees to use the tool. See Communication Plan tab. | All
Invest in employee training. | Educate employees on why a password management tool is necessary and the importance of cybersecurity. Highlight how the employee willl benefit. LastPass will protect the individual as an employee and a consumer. Use metrics and statistics to communicate the value (81% of breaches are password-related. Average cost of breach is nearly $4 million.). | All
Go mobile. | 56% of web traffic comes from a mobile device. The LastPass mobile app is not only easy to use, but will increase adoption. Encourage mobile use and train on the mobile product experience. | All
Commit to regular check in calls with your LastPass Team. | Attending regular LastPass meetings are critical to successful adoption. We will keep you updated on usage, best practices, and make recommendations. | All
Create and report on success metrics. | How can you measure success in LastPass? What metrics can LastPass help you track? What is important to you? | Client
Employee Training Best Practices
Schedule and record live trainings. | Where and when? Onsite, or via GoToMeeting? Lunch and learns? Record the live trainings to share later. Post recorded trainings where employees can find them, whether they weren't able to attend or just need a refresh of the material. | All
Leverage existing LastPass materials. | See the "Support and Training" tab for links for: - Tutorial videos - FAQs - Support resources - Recorded trainings - Handouts, flyers, and more. | Client
Incorporate materials in all email communications. | Remind employees where they can find handouts and support resources to help them get started with LastPass. | Client
Communication Strategy Best Practices
Customize the LastPass welcome email. | LastPass generates a default welcome email for users added to your Enterprise. Customize the content from the admin dashboard (in the Users tab, click Add User, Edit Preferences for the email, and select the Custom email option). | All
C-level executive announcement email. | After determining your executive sponsor, work with them to craft an email expressing excitement over LastPass, why it's an important initiative, and the benefits employees will receive by using the service. | Client
Determine a central repository for materials. | Determine your primary communication channel(s) and storage for documentation, recordings, and other materials. Intranet? OneDrive? | Client
Adapt training to your employees. | How do you train employees on other products? What works for your users? Hands-on? In-person training? OnDemand Videos? User Guides? | Client
Spread awareness with visual materials. | Use Posters, Flyers, Digital Signage and other visuals to raise awareness and drive interest. | All
Promote mobile usage. | Unless you are disallowing mobile access via policies, make sure users are aware of the benefits of taking LastPass with them on all of their devices, so they have their passwords no matter where they're working. | All
Identify internal champions. | Identify internal advocates for your LastPass deployment, whether people who are already using LastPass or are excited to use it. Reward them (t-shirts, gift cards, public recognition, etc) and point others to them as a resource for people who have questions about LastPass. | Client
Make it fun! | Launch a competition or activity, and announce a prize on best usage of LastPass. For example: The first team to achieve 100% adoption of LastPass wins a prize. | All

## 5-Communication Plan
Action Item | Description | Owner | Dates | Status | Notes
Pre-Launch Phase (Create awareness of LastPass)
Build awareness of LastPass. | Hang posters or distribute flyers around the office. Post on your intranet, digital signage, or employee blog. Build awareness of how LastPass will be easy, convenient, and save employees time. | Client
Train the trainers. | Conduct training for admins, helpdesk, or other employees that will need to support LastPass usage and adoption. Record training for reference. | All
Notify employees by email. | Send at least one email (including the executive sponsor email) to let users know you'll be providing a password manager that will save them time and make them more secure. | Client |  |  | Executive sponsor email template download
Phase One: Day 1-14 (Onboard initial group)
Identify and roll out to up to select groups. | We recommend groups such as IT, Legal, Marketing and HR - a cross-section of employees and technical experience. Ensure all policies are set up correctly (see the Deployment Plan), instructions are clear, and these groups are properly trained. This is our internal trial group. By rolling out to these groups first, this will get the attention of the other groups. In most cases this will build some anticipation. | All
Conduct training. | Present an overview of password management and the benefits of LastPass, with a hands-on demo of how LastPass works. If possible, let employees use their laptops to set up and start using their accounts. | All
Weekly Calls with stakeholders. | Review usage, collect feedback and suggestions, and review open items. | All
Kick off a challenge. | Communicate the competition, activity, and/or reward that you will use to drive adoption. | Client
Phase 1 wrap up report. | Was phase 1 successful? How did it meet success criteria? What could we do better? | All
Phase Two: Day 15-30 (Onboard the entire organization)
Roll out LastPass to the rest of the organization. | Send invites to all users, automating through your user directory where applicable. | All
Schedule follow-up trainings. | Whether virtual or on-site, host trainings that provide an overview of password management and how LastPass works. Record the trainings for reference. | Client
Weekly Calls with stakeholders. | Review usage, collect feedback and suggestions, and review open items. | All
Reinvite inactive users. | From the admin dashboard, review inactive users and send an email. Also identify employees with low usage and re-share training materials. | Client
Phase 2 wrap up report. | Was phase 2 successful? How did it meet success criteria? What could we do better? | LMI
Phase Three: Day 30-60 (Reinvite and continue training)
Send email to inactive users. | Notify any employees that have failed to activate their accounts. Understand hurdles to activation and work to address them. | Client
Reinvite non-active users. | From the admin dashboard, review inactive users and send an email. Also identify employees with low usage and re-share training materials. | Client
Reward the top X% of users with best usage. | Identify your top users and reward them (gift cards, t-shirts, etc.). If you conducted a challenge, announce the winners. | All
Bi-Weekly Calls w/stakeholders. | Review usage, collect feedback and suggestions, review open items. Are we on track with success metrics? | All
Create an user success story. | Who are your top 10 users? Why are they so successful? Create a story and share it. | All
End User Surveys. | Why are you not using it? What is working? What is not working? Do you know the value of LastPass? | Client
Schedule More training as-needed. | Schedule follow-up trainings to cover core and advanced LastPass features. Help employees activate their account and start seeing the benefit of saving, filling, generating and sharing passwords with LastPass. | All
Phase 3 wrap up report. | Was phase 3 successful? How did it meet success criteria? What could we do better? | LMI
Phase Four: Day 60-90 (Ongoing maintenance)
Send email to users who have not used LastPass. | From the admin dashboard, review inactive users and send an email. Also identify employees with low usage and re-share training materials. | Client
Monthly Calls with stakeholders. | Review usage, collect feedback and suggestions, review open items. Are we on track with success metrics? | All
Schedule More training as-needed. | Schedule follow-up trainings to cover core and advanced LastPass features. Help employees activate their account and start seeing the benefit of saving, filling, generating and sharing passwords with LastPass. | All
Phase 4 wrap up report | Was phase 4 successful? How did it meet success criteria? What could we do better? | LMI

## 6-Training Plan
Action Item | Details | Owner | Dates | Status | Notes
Pre-Training Questionnaire
Will users have their devices with them in the room (i.e. laptops, mobile phones)?
Will they already have the LastPass extension installed on their browsers? If not, do they have the proper permissions for download so that we can help them install onsite?
Are you mandating or encouraging the use of multi-factor of authentication? If so, which option(s)?
Are you mandating or encouraging the use of a personal linked LastPass account? If not, are you prohibiting the use of a personal linked account?
Are you allowing Shared Folders?
Are you allowing users to access their account from mobile devices?
Are you implementing SAML Single Sign-On with LastPass?
Training Preparation | Skilljar Lastpass training |  |  |  | Use the LastPass Self-Service Training Portal
Please send the welcome email immediately prior to training
If they have been invited before, please re-invite from the Admin Console >> |  |  |  |  | Two-ways to Reinvite users: From Dashboard > Reinvite All From Users > Select User > Select ellipsis> Reinvite user
Training Agenda
Why use LastPass? | > Benefits to the user and the employer
Introduction to LastPass basics | > Downloading LastPass > How LastPass works: local/offline, everywhere access, the security model > Creating an account and a strong master passphrase > Linking a personal account > Storing sites in the Enterprise account > Storing sites in the linked personal account > Registering for new sites > Hands-free login and multiple accounts on the same domain > Generating passwords > Updating passwords
Advanced LastPass features | >.Multi-factor authentication > Shared Folders > Creating and using notes > Creating and using form fill profiles > The LastPass security challenge > Mobile access for iOS and Android > Advanced settings

## 7-Dashboard
Insert screenshots of admin dashboard metrics to measure milestones and improvements during implementation and adoption

## 8-Resources
Administrator Resources
Welcome to LastPass Video (3 minutes) | https://mfa-support.lastpass.com/
Official LastPass Help Center >> Type your question | https://support.logmeininc.com/lastpass/
Admin Toolkit - Evaluation, Implementation, Awareness & Education | https://support.logmeininc.com/lastpass/help/use-the-lastpass-enterprise-admin-toolkit-lp010027
Quick Helpdesk Guide for LastPass Enterprise Admins | https://assets.cdngetgo.com/4e/97/3fc5c80943789edacaefefb30e1c/lastpass-ent-user-helpdesk-guide.pdf
Security Topics | https://www.lastpass.com/enterprise/security
>> Security Overview Flyer | https://assets.cdngetgo.com/69/c0/2cef992e48eeba015c85312f16ce/lastpass-encryption.pdf
>> Technical Whitepaper | https://assets.cdngetgo.com/60/be/323790b344bf8e631ecb033e4cad/lastpass-technical-whitepaper.pdf
Access the Enterprise Admin Console | https://support.logmeininc.com/lastpass/help/access-the-admin-console-lp010019
How to Add Enterprise Users | https://support.logmeininc.com/lastpass/help/how-to-add-enterprise-users-lp010044
>> Adding LastPass Users Manually | https://support.logmeininc.com/lastpass/help/manually-add-enterprise-users-lp010045
>> Use Directory Integrations for Automated Provisioning | https://support.logmeininc.com/lastpass/help/use-directory-integration-for-automated-provisioning-lp010046
>> LastPass Active Directory Connector | https://support.logmeininc.com/lastpass/help/set-up-the-lastpass-active-directory-connector-lp010057
>> Federated Login Experiences | https://support.logmeininc.com/lastpass/help/federated-login-experience-for-lastpass-enterprise-users-lp010056
View and Manage Enterprise User Settings | https://support.logmeininc.com/lastpass/help/view-and-manage-enterprise-user-settings-lp010048
Setup Single Sign-On (SSO) | https://support.logmeininc.com/lastpass/help/set-up-single-sign-on-for-lastpass-lp010079
Push Sites | https://support.logmeininc.com/lastpass/help/push-sites-to-users-lp010077
LastPass Enterprise Installing Software | https://support.logmeininc.com/lastpass/help/install-lastpass-software-using-the-admin-console-lp010069
Register for Live Admin and End-User Training Webinars | https://support.logmeininc.com/lastpass/help/free-live-training-lp010018 | https://register.gotowebinar.com/rt/7241816084495926283
Find Posters and Training Links > in Toolkit Under Awareness & Education | https://support.logmeininc.com/lastpass/help/use-the-lastpass-enterprise-admin-toolkit-lp010027
Understand How Super-Admin Password Reset Polilcy works | https://support.logmeininc.com/lastpass/help/reset-a-users-master-password-super-admin-lp010038
User Resources
Welcome to LastPass Video (3 minutes) | https://www.youtube.com/watch?v=oa9apKp_mHs&list=PLsXN_jRonzyctRhVdPUKGurKUArMEWcIM&index=2
Extended Getting Started--LastPass 101 (16 minutes) | https://support.logmeininc.com/lastpass/help/video-end-user-training-16-14-1309725811
Getting Started as an Enterprise User | https://support.logmeininc.com/lastpass/help/get-started-as-a-lastpass-enterprise-user-lp010051
End-User Instructional Setup Flyer > 1,2,3 - Go! Flyer | https://assets.cdngetgo.com/76/e6/094d0649443496d43e0ad7d1b175/lastpass-getting-started-flyer.pdf
End-User LastPass Made Easy Reference Flyer | https://assets.cdngetgo.com/a8/a7/7b14162c4af59f138b70bb307d27/end-user-reference-guide.pdf
LastPass for iOS | https://support.logmeininc.com/lastpass/help/lastpass-for-ios-lp060002
LastPass for Android | https://support.logmeininc.com/lastpass/help/lastpass-for-android-lp060001
Register for Live User Training Webinar | https://support.logmeininc.com/lastpass/help/free-live-training-lp010018 | https://register.gotowebinar.com/rt/8722554781298103307
Downloading and Installing LastPass for Users | https://support.logmeininc.com/lastpass/help/download-and-install-lastpass-lp010007
Manage Browser Extension Preferences (does not override policy) | https://support.logmeininc.com/lastpass/help/manage-browser-extension-preferences-lp010009
Manage LastPass Enterprise Shared Folders (Users) | https://support.logmeininc.com/lastpass/help/manage-lastpass-enterprise-shared-folders-users-lp010053
Manage Your Vault | https://support.logmeininc.com/lastpass/help/manage-your-vault-lp010015
How do I manage my site passwords? | https://support.logmeininc.com/lastpass/help/how-do-i-manage-my-site-passwords-lp010115
Require a Password Re-Prompt | https://support.logmeininc.com/lastpass/help/require-a-password-re-prompt-lp020009
Set Up Automatic Logins | https://support.logmeininc.com/lastpass/help/set-up-automatic-logins-lp020008
Disable Autofill for Sites | https://support.logmeininc.com/lastpass/help/disable-autofill-for-sites-lp020004
Use the Security Challenge | https://support.logmeininc.com/lastpass/help/use-the-security-challenge-lp030011
Training Resources
User Guide and Getting Started & Explore Features | https://support.logmeininc.com/lastpass
End User Training Video | https://www.youtube.com/watch?v=oa9apKp_mHs&list=PLsXN_jRonzyctRhVdPUKGurKUArMEWcIM&index=2 | https://support.logmeininc.com/lastpass/help/video-enterprise-user-demo-14-52-1309856441
All Training Videos | https://www.youtube.com/channel/UCFLeKmbS3mmvGjXvZ5hnfKw
LastPass Videos in other languages
Spanish | https://www.youtube.com/watch?v=BUavGENCSHk&list=PLsXN_jRonzydkVHGrmLfTgl5FPPf5GXsM
French | https://www.youtube.com/watch?v=aNrDCiYdews&list=PLsXN_jRonzycvvw9W6kTi_HuGIoqvoLik
German | https://www.youtube.com/watch?v=6hrxcoQsTwA&list=PLsXN_jRonzyf7RJyZhCDF6hRUUDBcm3ta