## Deployment Plan
Phase | Objective | Owner | Due Date | Tasks | Reference Materials | Est. Days to Complete
Set-up and Project Team Roll-out | Identify the LastPass Project Team |  |  | 1. Internal account manager(s): responsible for oversight and ongoing program management |  | 1
.. |  |  |  | 2. Internal security contacts: responsible for Policy configurations |  | 1
|  |  |  | 3. Internal System Administrators: responsible for the installation and configuration of directory sync |  | 1
|  |  |  | 4. Identify your Helpdesk Experts (maybe entire helpdesk) |  | 1
|  |  |  | 5. Schedule LastPass Introductory Demo for Project Team (See Resources tab) | https://support.logmeininc.com/lastpass/help/free-live-training-lp010018 | 1
| Provision Project Team |  |  | 1. Provision accounts for all members of the Project Team | https://support.logmeininc.com/lastpass/help/user-provisioning | 1
|  |  |  | 2. Then grant Admin rights to all members of the project team that require access | https://support.logmeininc.com/lastpass/help/admin-privilege
| Review App Download and User Provisioning Options |  |  | 1. Review User Provisioning Options and identify preferred method of installation on user devices | https://support.logmeininc.com/lastpass/help/user-provisioning | 1
|  |  |  | 2. Test user invite and download MFA app from app store | https://play.google.com/store/apps/details?id=com.lastpass.mfa
https://apps.apple.com/us/app/lastpass-mfa/id1465227096
| Explore Admin Console Available Features |  |  | 1. Determine which resources you plan to protect with MFA | https://www.lastpass.com/app-catalog | 1
|  |  |  | 2. Groups | https://support.logmeininc.com/lastpass/help/add-and-manage-lastpass-enterprise-groups-lp010064
|  |  |  | 3. Roles | https://support.logmeininc.com/lastpass/help/manage-lastpass-enterprise-user-roles
| Explore Integrations with Directories and/or SSO Providers |  |  | 1. Determine whether you have an existing user directory you plan to integrate with for provisioning |  | 1
2. Determine whether you have an existing SSO provider you plan to integrate with for protecting apps
| Review Policy Options-determine which ones to implement |  |  | 1. Review available policies | https://support.logmeininc.com/lastpass/help/video-add-an-access-policy-1-06 | 1
|  |  |  | 2. Customize authentication policies | https://support.logmeininc.com/lastpass/help/authentication-policies
|  |  |  | 3. Review Geofencing | https://support.logmeininc.com/lastpass/help/geofencing
|  |  |  | 4. Review IP restrictions | https://support.logmeininc.com/lastpass/help/ip-policy
| Reports |  |  | 1. Review Admin Reporting | https://support.logmeininc.com/lastpass/help/admin-audit | 1
| Testing by the Project Team |  |  | 1. Download the LastPass MFA mobile app on iOS or Android. |  | 3
|  |  |  | 2. Set up biometric authentication on LastPass MFA mobile app. | https://support.logmeininc.com/lastpass/help/video-multi-factor-authentication-3-00
3. Enable biometric authentication and contextual policies in the Admin Dashboard.
|  |  |  | 4. Configure MFA to a specific application. | **If Using LastPass Identity, also pair LastPass MFA with the LastPass account
5. Configure a Geofence
6. Whitelist and Blacklist an IP
7. Test login with biometrics.
8. Test login with and without contextual policies.
9. Automated account termination using directory sync option (AD Connector, Okta, Azure AD, etc).
| Communications/Internal Training |  |  | 1. Review the Communication Plan tab and Training Tab and agree on approach. |  | 4
2. Assign Communication Plan owner.
Small Test Group Rollout | Set-up Test Group (Superuser Pilot Group) |  |  | 1. Define Test Group participants. | Focus on creating a small testing group that includes people from multiple departments across your organization for a more accurate picture of user experience and to create department Super users that will be able to assist other users during the full roll-out. | 1
2. Inform Project Team of test group launch date and scope.
3. Define Project Milestones and Success Measurements for test group.
| Communications - Test Group |  |  | 1. Send email to all test group participants informing them of the upcoming roll out, the purpose of the program and corporate expectations. |  | 1
2. Highlight that they should expect an invite from LastPass in the next 24 hours.
| Test Group Launch |  |  | 1. Provision Test Group participants |  | 1
2. Conduct end user training
3. Customized training materials should steer the user to the support center and helpdesk personnel with questions.
| Communications - Company-wide Announcement |  |  | 1. Following Communication Plan tab, send communication to all employees informing them of the upcoming roll out, the purpose of the program, and corporate expectations |  | 1
2. Send out links for onboarding of users and other materials for self-training
| Monitoring for Participation and Compliance |  |  | 1. Check Admin reports for usage statistics among test group |  | 14
2. Conduct outreach/training for anyone not currently using
| Pilot Group Wrap-Up - Measure Beta Results |  |  | 1. Survey test group on ease of implementation, training and satisfaction ratings |  | 2
2. Make changes to the implementation strategy based on survey learnings
Company-wide Rollout | Communications - Launch Announcement and Training |  |  | 1. Following Communication Plan, send email to entire company (or all participants) informing them of the start of the roll out, the purpose of the program, corporate expectations, and educational material (FAQs, links to training videos, information on getting support) |  | 1
2. Highlight that they should expect a welcome email from LastPass in the next 48 hours
3. Schedule End User Training with CSM or Utilize weekly Live Trainings
| Launch |  |  | 1. Provision accounts for every target user |  | 14
2. Implement full end user training and education program
3. Check the Admin console reports for usage statistics and for compliance
4. Survey users on satisfaction ratings
| Review |  |  | 1. Conduct project end meeting to measure success on product delivery and adoption, agree on next steps, and pass on the project to the assigned CSM for ongoing support.

## Best Practices
Action Item | Description | Owner | Dates | Status | Notes
Top Adoption Drivers
Assign an Executive Sponsor. | We recommend selecting a C or V level Executive to champion LastPass MFA internally and receive regular reports of progress on the rollout. | Client
Make LastPass MFA mandatory. | Consider creating a company policy that all employees are mandated to use LastPass MFA. | Client
Hardwire LastPass MFA. | Make LastPass MFA a requirement for accessing essential apps and services. | Client
Integrate with your user directory or SSO provider. | By integrating with your existing directory, every employee can be automatically onboarded to LastPass MFA when they join the company, as well as off-boarded when they leave. You'll simplify day-to-day management for admins while spreading usage in the organization. If different than your user directory, integrating with your SSO provider ensures you protect business apps. | All
Use blacklisting or whitelisting to improve the experience. | For low-risk, everyday activities, reduce authentication requirements so users enjoy a simpler workflow without sacrificing security. | Client
Turn on geofencing. |  | Client
Formalize a communication strategy. | Develop a plan for raising awareness of LastPass MFa and training employees to use the tool. See Communication Plan tab. | All
Invest in employee training. | Educate employees on why multifactor authentication is necessary and the importance of cybersecurity. Highlight the unique features of LastPass MFA that will benefit the user. Use metrics and statistics to communicate the value (80% of breaches are password-related. Average cost of breach is nearly $4 million.). | All
Commit to regular check in calls with your LastPass Team. | Attending regular LastPass meetings are critical to successful adoption. We will keep you updated on usage, best practices, and make recommendations. | All
Create and report on success metrics. | How can you measure success in LastPass? What metrics can LastPass help you track? What is important to you? | Client
Employee Training Best Practices
Schedule and record live trainings. | Where and when? Onsite, or via GoToMeeting? Lunch and learns? Record the live trainings to share later. Post recorded trainings where employees can find them, whether they weren't able to attend or just need a refresh of the material. | All
Leverage existing LastPass materials. | See the "Resources" tab for links for: - Tutorial videos - Support resources - Admin resources | Client
Incorporate materials in all email communications. | Remind employees where they can find training and support resources to help them get started with LastPass. | Client
Communication Strategy Best Practices
C-level executive announcement email. | After determining your executive sponsor, work with them to craft an email expressing excitement over LastPass MFA, and why it's an important initiative. | Client
Determine a central repository for materials. | Determine your primary communication channel(s) and storage for documentation, recordings, and other materials. Intranet? OneDrive? | Client
Adapt training to your employees. | How do you train employees on other products? What works for your users? Hands-on? In-person training? OnDemand Videos? User Guides? | Client
Spread awareness with visual materials. | Where possible, use Posters, Flyers, Digital Signage and other visuals to raise awareness and drive interest. | All

## Communication Plan
Action Item | Description | Owner | Dates | Status | Notes
Pre-Launch Phase (Create awareness of LastPass MFA)
Train the trainers. | Conduct training for admins, helpdesk, or other employees that will need to support LastPass MFA usage and adoption. Record training for reference. | All
Notify employees by email. | Send at least one email to let users know the company will be using a new MFA solution. | Client
Build awareness of LastPass MFA. | Post on your intranet, digital signage, or employee blog. Build awareness of what MFA is, how it improves security, and the unique benefits of LastPass MFA. | Client
Phase One: Day 1-14 (Onboard initial group)
Identify and roll out to select groups. | We recommend groups such as IT, Legal, Marketing and HR - a cross-section of employees and technical experience. Ensure all policies are set up correctly (see the Deployment Plan), instructions are clear, and these groups are properly trained. This is our internal trial group. By rolling out to these groups first, this will get the attention of the other groups. In most cases this will build some anticipation. | All
Conduct training. | Present an overview of MFA and the benefits of LastPass, with a hands-on demo of how the app works. If possible, let employees set up the app and practice logging in during training. | All
Weekly Calls with stakeholders. | Review usage, collect feedback and suggestions, and review open items. | All
Phase 1 wrap up report. | Was phase 1 successful? How did it meet success criteria? What could we do better? | All
Phase Two: Day 15-30 (Onboard the entire organization)
Roll out LastPass MFA to the rest of the organization. | Send invites to all users, automating through your user directory where applicable. | All
Schedule follow-up trainings. | Whether virtual or on-site, host trainings that provide an overview of MFA and how LastPass works. Record the trainings for reference. | Client
Weekly Calls with stakeholders. | Review usage, collect feedback and suggestions, and review open items. | All
Reinvite inactive users. | From the admin dashboard, review inactive users and send an email. Also identify employees with low usage and re-share training materials. | Client
Phase 2 wrap up report. | Was phase 2 successful? How did it meet success criteria? What could we do better? | LMI
Phase Three: Day 30-60 (Reinvite and continue training)
Send email to inactive users. | Notify any employees that have failed to activate their accounts. Understand hurdles to activation and work to address them. | Client
Reinvite non-active users. | From the admin dashboard, review inactive users and send an email. Also identify employees with low usage and re-share training materials. | Client
Bi-Weekly Calls w/stakeholders. | Review usage, collect feedback and suggestions, review open items. Are we on track with success metrics? | All
End User Surveys. | Why are you not using it? What is working? What is not working? Do you know the value of LastPass MFA? | Client
Schedule More training as-needed. | Help remaining employees activate and use LastPass MFA. | All
Phase 3 wrap up report. | Was phase 3 successful? How did it meet success criteria? What could we do better? | LMI
Phase Four: Day 60-90 (Ongoing maintenance)
Send email to users who have not used LastPass MFA. | From the admin dashboard, review inactive users and send an email. Also identify employees with low usage and re-share training materials. | Client
Monthly Calls with stakeholders. | Review usage, collect feedback and suggestions, review open items. Are we on track with success metrics? | All
Schedule More training as-needed. | Ensure training is incorporated into employee onboarding. | All
Phase 4 wrap up report | Was phase 4 successful? How did it meet success criteria? What could we do better? | LMI

## Training Plan
Action Item | Details | Owner | Dates | Status | Notes
Pre-Training Questionnaire
Will users have their devices with them in the room (i.e. laptops, smartphones)?
Will they already have downloaded the LastPass MFA app?
For which apps/services are you requiring the use of MFA?
Is LastPass MFA being used with other LastPass solutions?
Are there specific policies/restrictions that will go into effect with MFA?
Training Preparation
Please send the welcome email immediately prior to training
If they have been invited before, please re-invite from the Admin Console
Training Agenda
Why use LastPass MFA? | > Benefits to the user and the employer > Value of biometrics and contextual factors for both security and user experience > Going beyond traditional push notifications for added security that doesn't increase friction
Installing LastPass MFA | > Navigating to the App Store(s) > Downloading the App > Pairing the App with the Account > Setting Up Biometrics > Enable Push Notifications > Enable Location
Using LastPass MFA | > Signing in to an App > Viewing or Changing App Settings
Common Troubleshooting | > Lost or Forgotten Device > Resetting Biometrics > Transferring to a New Phone
Optional Features | > Create a personal LastPass Password Management account. > Pair LastPass MFA with LastPass account. > Log in to LastPass and submit multi-factor authentication prompt. > Download and log in to LastPass from the mobile app (iOS, Android, Windows Phone).

## Resources
Administrator Resources
LastPass Support Center | https://support.logmeininc.com/lastpass
Administrator
>>> Directory Integration | https://support.logmeininc.com/lastpass/help/use-directory-integration-for-automated-provisioning-lp010046
>>> Universal Proxy Installation | https://support.logmeininc.com/lastpass/help/universal-proxy-installation
>>> Universal Proxy Installation - Windows | https://support.logmeininc.com/lastpass/help/universal-proxy-installation-windows
User Management
>>> User Provisioning | https://mfa-support.lastpass.com/admins/user-management/user-provisioning/
>>> Admin Privileges | https://mfa-support.lastpass.com/admins/user-management/admin-privilege/
>>> Manage Groups | https://mfa-support.lastpass.com/admins/user-management/manage-groups/
>>> Manage Roles | https://mfa-support.lastpass.com/admins/user-management/manage-roles/
Application Management
>>> Add SSO Apps | https://support.logmeininc.com/lastpass/help/add-lastpass-sso-apps
>>> SSO App Catalog | https://support.logmeininc.com/lastpass/help#lastpass-lastpass-app-integrations
>>> Edit SSO Apps | https://support.logmeininc.com/lastpass/help/manage-lastpass-sso-apps
>>> Assign SSO Users | https://support.logmeininc.com/lastpass/help/manage-lastpass-sso-apps
>>> Add Legacy Apps and VPNs | https://support.logmeininc.com/lastpass/help/add-legacy-apps-and-vpns
VPN
>>> Checkpoint | https://support.logmeininc.com/lastpass/help/check-point-vpn-configuration
>>> Cisco ASA | https://support.logmeininc.com/lastpass/help/asa-cisco-configuration-with-universal-proxy
>>> PulseSecure | https://support.logmeininc.com/lastpass/help/pulsesecure-vpn-integration
Policy Management
>>> Access Policy Management | https://mfa-support.lastpass.com/admins/policy-management/access-policy/
>>> Authentication Policies | https://mfa-support.lastpass.com/admins/policy-management/authentication-policies/
>>> Geofencing | https://mfa-support.lastpass.com/admins/policy-management/geofencing/
>>> IP Policy | https://mfa-support.lastpass.com/admins/policy-management/ip-policy/
Admin Report Audits | https://support.logmeininc.com/lastpass/help/admin-audit
Register for Live Admin and End-User Training Webinars | https://support.logmeininc.com/lastpass/help/free-live-training-lp010018 | https://register.gotowebinar.com/rt/7241816084495926283
LastPass Technical Whitepaper | https://assets.cdngetgo.com/60/be/323790b344bf8e631ecb033e4cad/lastpass-technical-whitepaper.pdf
User Resources
Tutorial Videos | https://support.logmeininc.com/lastpass/help/video-multi-factor-authentication-3-00
User Troubleshooting | https://support.logmeininc.com/lastpass/help/lastpass-mfa-troubleshooting
Contact Support | https://support.logmeininc.com/lastpass/help/how-do-i-contact-customer-support-for-lastpass-lp010121?c_prod=care&c_name=contactus&c_cmp=help
MFA App Activation | https://support.logmeininc.com/lastpass/help/lastpass-mfa-app-activation
Login with LastPass MFA | https://support.logmeininc.com/lastpass/help/how-do-i-authenticate-using-the-lastpass-mfa-app
MFA App Setting | https://support.logmeininc.com/lastpass/help/manage-lastpass-mfa-app-settings
Register for Live User Training Webinar | https://support.logmeininc.com/lastpass/help/free-live-training-lp010018 | https://register.gotowebinar.com/rt/8722554781298103307