## Deployment Project Plan
LastPass Implementation Project Management Plan
Phase | Objective | Tasks | Owner | Due Date | Reference Materials
Getting started | Identify the LastPass Project Team | 1. Determine your internal account administrator(s): responsible for oversight of implementation and ongoing program management
2. Identify internal security contact(s): responsible for LastPass Policy configurations
3. Identify internal system administrator(s): responsible for the installation and configuration of directory sync
4. Identify your helpdesk and training experts: responsible for training and helping support end-users
|  | 5. Update Company Profile in the Admin console with Billing address and Contacts |  |  | Support article: Manage Company Profile
|  | 5. Get familiar with LastPass. Learn how to use LastPass as an administrator and an end-user |  |  | Video: LastPass Business account Demo (30 minutes)
|  | Embark LastPass Admin training portal |  |  | Video: LastPass Admin Dashboard (1 min)
|  | Embark LastPass End User training portal |  |  | Video: LastPass End User Demo (14 minutes)
|  | Explore LastPass videos |  |  | Support: Get Started, Explore Features, Admin Tools
| Provision Project Team | 1. Manually provision accounts for all members of the LastPass Project Team |  |  | Support article: How to Add Users
|  | 2. Grant Admin rights to members of the project team that require admin access |  |  | Support article: View and Manage User Settings
| Explore LastPass Features | Explore LastPass Features |  |  | Support article: Overview of LastPass Plan features
|  | • Sharing |  |  | Support article: Use the Sharing Center
|  | • Shared Folders Feature |  |  | Support article: About LastPass Shared Folders
|  | --Manage Shared Folders Admin |  |  | Support article: View and Manage LastPass Shared Folders (Admins)
|  | --Manage Shared Folders User |  |  | Support article: Manage LastPass Shared Folders (Users)
|  | • Linked Personal Accounts |  |  | Support article: Link or Unlink Your Personal Account to/from LastPass business account
|  | • Mobile device |  |  | Support article: How do I use LastPass on my mobile device?
|  | • Form Fill |  |  | Support article: Manage Your Form Fills
|  | • Secured Notes |  |  | Support article: Manage Your Secure Notes
|  | • Secure Passwords |  |  | Support article: Generate Secure Passwords
|  | • Password Recovery options |  |  | Support article: Recover Your Lost Master Password
Pre-deployment Admin Configurations, Settings, and Tools | Automated Directory Provisioning and Deprovisioning accounts | 1. Review automatic provisioning and directory integration options (LastPass AD connector, API, Azure, Okta, OneLogin) |  |  | Support article: Use Directory Integrations for Automated Provisioning
|  | • Syncing on prem Active Directory with LastPass |  |  | Video: LastPass Active Directory Connector Demo
|  | 2. Determine which directory integration option is best suited for your environment or if you will manually provision accounts |  |  | Support article: How to Add Users
|  | 3. Determine whether to federate LastPass logins with you organization's Active Directory account or create accounts with a unique master password. |  |  | Support article: Federated Login Experience for LastPass Users
|  | • Limitations for Federated users |  |  | Support article: What are the limitations for federated LastPass users?
|  | • Federation with Okta |  |  | Support article: Set Up Federated Login for LastPass Using Okta
|  | • Federation with Azure |  |  | Support article: Set Up Federated Login for LastPass Using Azure Active Directory
|  | • Federation with ADFS |  |  | Support article: Set Up Federation Services (AD FS) for LastPass
| Install LastPass Browser Extension on devices | 1. Review software installation and download options (push install package, browser ext., or manually download) |  |  | Support article: Download and Install LastPass
|  | 2. Identify preferred method for installation on user devices |  |  | Support article: How to deploy LastPass web browser extensions
Support article: Install LastPass Software Using the Admin Console
|  | 3. Consider how you will restrict unacceptable means of password saving/sharing after LastPass deployed. |  |  | Support article: How to disable my web browser's password manager
| Admin Policy Configurations | 1. Consider your local and global security policy settings |  |  | Support article: Local and Global Security Options
2. Determine how you want users to interact with LastPass: Login/Logoff, Account Restrictions, Authentication, Feature usage (Sharing, Linked Accounts, Mobile access), etc.
3. Review LastPass general policies with your security team and determine which ones to implement. See the General Policies worksheet on tab 2 for a complete policy list and best practice considerations
|  | 4. Review how to add and manage policies from the Admin Console |  |  | Support article: Add and Manage Password Manager Policies
5. Configure policies in the Admin console
| Applications Configuration | 1. Audit company tools and sites used internally
2. Pre-load User Vaults with Single Sign-On Applications or Password Apps
|  | • Explore and Add LastPass SSO apps |  |  | Support article: SSO Admin toolkit
|  | • Explore and Push sites directly to users vaults via the Admin console |  |  | Support article: Push Sites to Users Vaults
| Advanced Configurations | 1. Review Advanced options |  |  | Support article: Advanced Options
|  | • URL rules |  |  | Support article: How to manage URL Rules from the Admin console
|  | • Global Equivalent Domains |  |  | Support article: Admin Management of Global Equivalent Domains
|  | • Global Never and Global Only URLs |  |  | Support article: Admin Management of Global Never and Global Only URLs
|  | • Admin Management of Master Passwords |  |  | Support article: Admin Management of Master Passwords
|  | • Splunk Integration |  |  | Support article: How to integrate Splunk with LastPass
|  | • Enabling Multifactor Authentication |  |  | Support article: Enable Multifactor Authentication (Admins)
Support article: Admin Management of Multifactor Authentication Options
2. LastPass API
|  | 3. Federated Login |  |  | Support article: Federated Login user experience
Support article: How to convert a user to a Federated User
| Email Notifications | 1. Configure Email Notifications to monitor usage, security and to automate emails to end users |  |  | Admin Console: Email Notifications
Support article: Manage Email Notifications for LastPass
| Reporting | 1. Review Admin Console Reporting tool |  |  | Support article: Generate Reports
2. Test End-User, Admin, Security and Login reports
| Other Admin Console topics | 1. Adding and Managing User Groups |  |  | Support article: Add and Manage LastPass Groups
|  | 2. Managing User Roles |  |  | Support article: Understanding User Types
Support article: Manage LastPass User Roles
Pre-deployment Testing | Testing by the Project Team | 1. Test the top sites and applications utilized by your employees to ensure they are functioning seamlessly
2. Enable and test any SAML or Push site apps that you intend to use in full roll-out (if applicable)
3. Test all policies for proper configuration
4. Test any Equivalent Domains, Whitelists or Blacklists that you have enabled to ensure proper set-up/mapping
Pre-deployment Communication & Training Development | Create Communication materials to spread awareness and set expectations of usage | 1. Assign an ownder to Communication and Training planning. |  |  | Communication tool: LastPass Admin Awareness toolkit
| Establish training plan to meet needs of users at multiple levels | 2. Review Communication Plan, Training Plan and Adoption Best Practices tabs and agree on initiatives.
|  | 3. Determine if you will customize your Welcome email template or use Standard? --Let your CSM know if you customize it so your template can be approved. |  |  | Download and review Welcome to LastPass email template
|  | 4. Create a customized activation / installation guide to help users self-guide through the account creation process. |  |  | Support article: Account activation steps through Welcome email
Support article: Federated Login Experience for LastPass Users
5. Create internal repository of resources and support information for FAQs (SharePoint, Slack or Teams channel).
Pilot Group Testing Rollout | Set-up Small Test Pilot Group | 1. Define Test Group participants for pilot launch. |  |  | Create a pilot group that includes people from multiple departments and levels within your organization for a more accurate picture of user experience, and to create department champions that will be able to assist other users during the full roll-out.
2. Inform Project Team of test group launch date and scope.
3. Define Project Milestones and Success Measurements for test group. • Feedback on account activation/installation process • Feedback on training experience • Feedback on basic product • Usage day-day (adding passwords, sharing, generating passwords, etc.)
| Communications - Test Group | 1. Send email to all test group participants informing them of the upcoming roll out, the purpose of the program and corporate expectations.
2. Highlight that they should expect a welcome email from LastPass in the next 24 hours.
|  | 3. Highlight steps for users how to get started, creating their account, and how to find help should they need it |  |  | Support article: Get Started as a LastPass User
| Test Group Launch | 1. Provision Test Group participants
2. Conduct end user training or provide self-service resources
| Pilot Group Wrap-Up - Gather Feedback | 1. Survey test group on ease of implementation, training and satisfaction ratings |  |  | Return on Investment (ROI) Calculator
2. Check Company Security Score and other performance indicators in Admin Console
3. Capture total number of logins and calculate savings
4. Make changes to the implementation strategy based on survey learnings
Send Communication and Publish Training | Communications - Company-wide Announcement | 1. Follow your established communication plan and send communications to all employees informing them of the upcoming roll out, the purpose of the program, and corporate expectations |  |  | Support Article: Email Templates for New LastPass Users
2. Send email to all end-users that includes training materials
Company-wide Deployment | Communications - Launch Announcement and Training | 1. Following your established communication plan, send email to entire company (or all participants) informing them of the start of the roll out, the purpose of the program, and set corporate expectations, provide educational and training material |  |  | Communication tool: Secure password management made easy
|  | 2. Highlight that they should expect a welcome email from LastPass in the next 48 hours |  |  | Communication tool: LastPass Admin Education toolkit
3. Include a customized activation / installation guide to help users self-guide through the account creation process
4. Inlcude link(s) to internal repository of resources (SharePoint, Slack or Teams channel) that includes FAQs, links to training videos, support articles, and additional information for end-user success
|  | 5. Schedule End User Training or Utilize weekly Live Trainings |  |  | Training tool: Register for Live End User Training
|  | Embark LastPass End User training portal |  |  | Training tool: Use the LastPass Self-Service Training Portal
|  | Explore LastPass videos |  |  | Support article: Get Started as a LastPass User
|  | End user toolkit |  |  | Video: End User Training (16 min)
Communication tool: Getting Started in 4 Easy Steps
| Launch | 1. Provision accounts for every target user. Based upon the size of your organization, consider deploying by department or moving forward with a companywide rollout
|  | 2. Implement full end user training and education program |  |  | Training tool: Download LastPass End User training presentation
Training tool: Download LastPass End User Training Script
3. Check the Admin console notifications report for usage statistics and for compliance
4. Survey users on satisfaction ratings and impact on productivity
| Monitoring for Participation and Compliance | 1. Check the notifications report for usage statistics among test group
2. Conduct outreach/training for anyone not currently using
| Review | 1. Conduct project end meeting to measure success on product delivery and adoption, agree on next steps, and pass on the project to the ongoing support admin.
Ongoing Management and Support | Lifecycle Adoption and Usage Monitoring | 1. Run weekly Reports to measure adoption, usage and security |  |  | Support article: Generate Reports
2. Send milestone communication emails every 30 days to executive sponsor with progress and compliance updates.
3. Perform active outreach to users who are not actively using LastPass and investigate roadblocks to adoption.
4. Provide additional training and workshops to assist users with poor usage.
5. Integrate LastPass to your new employee onboarding program.

## General Policies
# | Category | Policy | Description | Considerations | Value | Apply To: All Inclusive – Only these users/groups Exclusive – All except these users/groups | *Does not apply to Federated Login?*
1.01 | Default | Block TOR Access | Restrict logins to LastPass accounts from The Onion Router (TOR) exit node IPs. | Default policy. We recommend keeping this policy enabled. | Enabled | All
1.02 | Default | Remember Master Password | Permit users to allow their LastPass browser extension to remember their master password. When enabled, users have the option to 'Remember master password' upon login to LastPass. | Default policy. As a best practice we recommend you delete/disable this policy. Remembering the password weakens the security for that user. | Enabled | All | *Does not apply to Federated Login*
1.03 | Default | Prohibit login from jailbroken phones | Prohibit users from logging in to LastPass on jailbroken iOS and Android devices.
1.04 | Default | Minimum character sets in master password | Force users to create a master password that includes at least this many different character sets. Once enabled, users with a master password using too few character sets are prompted to change their master password. Value: 1 (default), 2, 3, or 4 For example: enter value of 3 to force master passwords with at least one character from any three of the four character sets: uppercase, lowercase, numeric, and special (!#$,^ and similar). | As a best practice we recommend you follow your established AD password policy for length and complexity. |  |  | *Does not apply to Federated Login*
1.05 | Default | Prohibit reuse of old master passwords | Prohibit users from re-using recent master passwords. Value: The number of historical passwords to check against. | Default policy. As a best practice we recommend increasing the value from 1 to at least 5. Ideally, you want users to always use a new one, not recycle a few. | 1 | All | *Does not apply to Federated Login*
1.06 | Default | Apply parent account MFA policy | Apply the parent account's multifactor authentication requirements to linked personal accounts. | Default policy. If you don't want your multi-factor authentication to "impose" upon an employee's linked personal LastPass account, you can disable this policy. | Enabled | All | *Does not apply to Federated Login*
1.07 | Default | Notify admins upon user lockout | Send an email to the specified addresses when an account is temporarily locked out due to failed login attempts. Value: Enter email addresses, separated by commas. | Default policy. We recommend keeping this policy enabled, but review the value. The default value is the admin who created the account so you may want to edit this value. If this policy is deleted/disabled there is no way to unlock a user before the defined lockout period is over. | Enabled | All | *Does not apply to Federated Login*
1.08 | Default | Pre-Create Sharing Key | When creating user accounts server-side, automatically create and encrypt the sharing key that allows users to share items with others. Without this policy, users must log in to the browser extension to generate the key and share. Note: The sharing key will be created server-side, as opposed to client-side upon user login. It is immediately encrypted using the user's temporary password and is never stored in plaintext. | Default policy. We recommend keeping this policy enabled. | Enabled | All
1.09 | Default | Log mobile activity | Gather data about password access and site fill events for use in reporting. | Default policy. We recommend keeping this policy enabled. | Enabled | All
1.1 | Default | Show Master Password Strength | Collect and report data about the strength of your users' master passwords. | Default policy. We recommend keeping this policy enabled. | Enabled | All | *Does not apply to Federated Login*
1.11 | Default | Show Security Challenge Score | Upon user login, run the security challenge in the background and report the results. | Default policy. We recommend keeping this policy enabled. | Enabled | All
2.01 | Recommended | Account Logoff on Browser Close | Automatically log users out of their LastPass account when they close their browser. This forces users to log in each time they re-open their browser. This also prevents users from setting this policy themselves in their browser extensions. | It is a best practice to enable an account logoff policy. When this policy is enabled you will override the user's General Security Log Off Preferences. By default there are no log off policies configured and users can configure their own logoff preferences if they setup up their account securely.
2.02 | Recommended | Length of master password | Force users to create a master password that includes at least this many characters. Any user attempting to save a master password that uses too few characters is prompted to meet the requirement. Value: The required number of characters. Values must be greater than or equal to 8. To have a different limit for multifactor, specify a second number, separated by a comma (for example, 12,9). | As a best practice we recommend you follow your established AD password policy guidelines for length and complexity. |  |  | *Does not apply to Federated Login*
2.03 | Recommended | Length of site passwords | Force the password generator to suggest passwords with a minimum number of characters on specific sites. Value: Enter each domain, separated by commas, followed by equals (=) and the minimum number of characters. Use white space to separate multiple entries. Keep in mind there is no way to force users to actually submit the suggested password. For example: twitter.com=20 google.com,gmail.com=15
2.04 | Recommended | Prohibit Sharing Except for Shared Folders | Only allow sharing via the Shared Folders. This can further be limited to internal sharing within your organization's managed users when you also Enable the Prohibit Shared Folders Outside Enterprise policy under the Account Restrictions category. | As a best practice we recommend you enable this policy. When enabled it removes the option for users to share individual items, requiring shared items to be shared in a folder. This gives more auditability and accountability to sharing in your organization, and the option to give admins elevated super admin control over shared credentials if needed.
2.05 | Recommended | Require Master Password Change | Force users to change their master password after this many days. Value: The number of days between master password resets. This is recommended to be set at 90 days if you do not require multifactor usage, and 365 days if you require multifactor. To have a different limit for multifactor, specify a second number, separated by a comma (For example: 90,365). | As a best practice we recommend users change their master password every 90 days when there is no multifactor and every 180-365 days when multi-factor authentication is enforced. |  |  | *Does not apply to Federated Login*
2.06 | Recommended | Require any MFA (multifactor) option after grace period | Require users to enable a multifactor authentication option a specified number of days after account creation. To define the list of valid multifactor options available to users, go to Advanced > Enterprise Options > Multifactor Options in the Admin Console. Currently available options: LastPass Authenticator, YubiKey, LastPass Sesame, Google Authenticator, Toopher, Duo Security, SecureAuth, Transakt, Salesforce Authenticator, RSA SecurID, and Symantec VIP. Note: Fingerprint and Grid can not be managed through require use policy. | If requiring multifactor authentication with a grace period after account creation please ensure users are aware of the authentication process and how their login will change after the specified number of days. You may also consider the Require use of any MFA option policy in the Multifactor category to enforce MFA at the time of account creation or for existing accounts at their next login. |  |  | *Does not apply to Federated Login*
2.07 | Recommended | Permit super admins to access shared folders | Invisibly share all shared folders in your enterprise with authorized admins. Click 'Edit Users' to add admins. To disable the ability to add or change this policy, contact LastPass. Shared folders that existed prior to setting this policy are assigned the next time a user with 'Can Administer' access to that folder logs back in to LastPass. | As a best practice we always recommended enabling this policy. This policy requires set-up before elevated admin of all shared folder access is available.
2.08 | Recommended | Permit super admins to reset master passwords | Allow selected admins to reset the master password of any user in your enterprise. Click 'Edit Users' to add admins. Users must log in to the browser extension at least once to capture the encryption key that makes admin reset possible. Security tip: Always protect accounts with 'super admin' rights with multifactor authentication. While not recommended, you can specify multiple admins by separating their usernames by comma, space, or semicolon. To disable the ability to add or change this policy, contact LastPass. | As a best practice we always recommended enabling this policy. This policy requires set-up before elevated password reset admin access is available. Understand how this policy works review the following documentation: https://support.logmeininc.com/lastpass/help/reset-a-users-master-password-super-admin-lp010038
2.09 | Recommended | Notify admins upon account recovery | Send an email to the specified addresses when the account recovery option is used. Value: Enter 1 to send when an end users requests account recovery. Enter 2 to send when account recovery is successfully completed and the user re-sets their master password. Enter 1,2 for both options. For example: 1,2,admin@acme.com,admin2@acme.com | As a best practice we recommended enabling this policy. |  |  | *Does not apply to Federated Login*
2.1 | Recommended | Require PIN | Force users to enter a PIN code when they open the mobile app. | As a best practice we recommended enabling this policy. Requiring use of a PIN means users will be required to set up an 'alternative' unlock method. The default lock for the mobile app is 5 minutes. Once a PIN is set users can replace it with their mobile's supported biometric method.
2.11 | Recommended | Check for Compromised User Accounts | When performing a background security scan, check each username against a database of known third-party security breaches. If the username associated with a login is potentially at risk, an email is sent to the user identifying the compromised website and recommending preventative measures. | As a best practice we recommended enabling this policy. Read more about breach detection: https://support.logmeininc.com/lastpass/help/what-is-breach-detection-in-lastpass
3.01 | Access Controls | Restrict Access by IP Address | Use IP address restriction to allow access only from approved IP addresses or ranges. Value: Enter each allowed IP address or partial IP address, separated by white space. For example: 71.126.154. 128.8. 120.0.0.1 would allow login from any address in 71.126.154.*, 128.8.*.* and 120.0.0.1. A matching DNS restriction or country restriction also allows entry. We also support CIDR Notation. For example: 61.12.56.0/24 allows any address in 61.12.56.* to log in.
3.02 | Access Controls | Restrict Access by IP Address (Mobile Excluded) | Use IP address restriction (mobile excluded) to allow users of a mobile app to access their accounts from any IP address, but otherwise allow access only from approved IP addresses or ranges. Value: Enter each allowed IP address or partial IP address, separated by white space. For example: 71.126.154. 128.8. 120.0.0.1 would allow login from any address in 71.126.154.*, 128.8.*.* and 120.0.0.1.
3.03 | Access Controls | Restrict Access by Reverse DNS | Create a list of domains from which users are permitted to log in to LastPass. Value: Enter permitted domain names, separated by white space. For example: comcast.com comcast.net verizon.net This allows users to log in when the reverse DNS ends with comcast.com, comcast.net or verizon.net. Any matching IP address allows entry. A matching IP restriction or country restriction also allows entry.
3.04 | Access Controls | Restrict Access by Country | Only allow login to LastPass from specified countries. Value: Enter the two-character domain abbreviation for each permitted country, separated by white space. For example: US CA This allows users to log in when the country code for their IP is in the United States or Canada. Any matching country code allows entry. A matching IP restriction or DNS restriction also allows entry. For a list of country codes, see https://lastpass.com/listcountrycodes.php
3.05 | Access Controls | Prohibit Account Recovery | Prohibit users from using the account recovery process to access LastPass without their master password. Caution: When this policy is enabled, account recovery is impossible unless the 'Permit super admins to reset master passwords' policy is enabled. |  |  |  | *Does not apply to Federated Login*
3.06 | Access Controls | Prohibit Offline Access | Prohibit users from logging in without a network connection. We do not recommend this options since user data will no longer be stored locally on the device, thus preventing access to LastPass services when connectivity is lost. |  |  |  | *Does not apply to Federated Login*
3.07 | Access Controls | Prohibit Account Access on Mobile Devices | Prohibit users from accessing their LastPass account from a mobile device and m.lastpass.com. Upon attempted access, users are informed that the action is prohibited by policy.
3.08 | Access Controls | Prohibit login from 'Denied' devices (unless approved by user) | Only allow login to LastPass accounts from 'Allowed' mobile devices. Learn how to allow or deny access here: https://support.logmeininc.com/lastpass/help/manage-account-settings-lp010017#Mobile | If policy is enabled Mobile devices need to be approved by the user in their own vault > Account settings > Mobile Devices.
3.09 | Access Controls | Prohibit login from 'Denied' devices unless approved (by admin) | Only allow login to LastPass accounts from 'Allowed' mobile devices or those devices approved on demand by an admin in the Admin Console. | If policy is enabled and user tries to log in from a denied mobile device they will get a notification saying the admin needs to approve the login. An admin would then need to approve the mobile device from the Admin Console > Users > select user > from Trusted Mobile devices will need to enable the device.
3.1 | Access Controls | Restrict login attempts before lockout | Allow this many failed login attempts before locking a user's account and preventing further attempts for the time period set in the 'Lockout period' policy. Value: Set number of allowed attempts value between 3 and 8. For example: a value of 3 results in lockout on the fourth failed attempt. | Best practice is to set a value of allowed attempts between 3 and 8. If left disabled system value is 5.
3.11 | Access Controls | Lockout period | Upon exceeding the number of allowed failed login attempts, a user's account remains locked for this many minutes before they can attempt login. Value: Set number value between 10-60 (minutes). | Best practice is to set a value between 10-60 minutes. If left disabled system value is 15 minutes.
3.12 | Access Controls | Disable Email Verification for New Devices | When a user logs in to LastPass from new device, do not force them to prove their identity via email verification link. Caution: We do not recommend enabling this policy. It significantly reduces the security of users' LastPass accounts.
3.13 | Access Controls | Override Session Lifetime | Expire all user sessions after this many hours, regardless of activity. Users will be warned two minutes before their session expires. Value: 1-9999 (hours) | This policy will effect mobile users as well.
3.14 | Access Controls | Account Logoff on Browser Idle (extension) | Automatically log users out of their LastPass account after their browser remains idle for this many minutes. This also prevents users from setting this policy themselves in their browser extensions. Value: 0-9999 (minutes). IMPORTANT: Your identity provider settings may override this policy for your federated users. | Best practice is to enable an account logoff policy. When this policy is enabled you will override the user's General Security Log Off Preferences. By default there are no log off policies configured and user is able to configure their own logoff preferences. Consider enabling this policy to ensure users are logged out of LastPass after being idle for an extended period of time since not all users will close their browsers at the end of the day.
3.15 | Access Controls | Account Logoff on Computer Lock | This policy allows you to override user's browser setting to logoff the user on computer lock. **LastPass for Windows must be running in order for this policy to work. | Specific to LastPass for Windows application
3.16 | Access Controls | Account Logoff on Screensaver | This policy allows you to override user's browser setting to logoff the user on computer lock. **LastPass for Windows must be running in order for this policy to work. | Specific to LastPass for Windows application
3.17 | Access Controls | Account Logoff on Shutdown/Logoff | This policy allows you to override user's browser setting to logoff the user on computer lock. **LastPass for Windows must be running in order for this policy to work. | Specific to LastPass for Windows application
3.18 | Access Controls | End existing sessions on login | After login from a new location, based on IP address, you'll be logged out of existing sessions in most cases (your browser session must be open and polling enabled). If you close your browser session without logging out of LastPass, this feature still protects you. For example, your browser is closed at work, and you log in from home. You return to work and are forced to log in again. | Consider enabling this policy to prevent users from being logged in to multiple sessions of LastPass at the same time in different locations and on different devices (including mobile).
3.19 | Access Controls | Account logoff (website) | Automatically log users out of LastPass.com after the selected period of time. This also prevents users from setting this policy themselves (Account Settings > Website Auto-Logoff). Value: 5-20160 (minutes). IMPORTANT: Your identity provider settings may override this policy for your federated users. | As a best practice we recommended enabling this policy. Enabling this policy and setting a value between 5-20160 minutes helps protect user's vaults. Typically, users don't use their online vault unless they are on a shared machine without the extension installed. Setting a value here ensures users will be logged out of website if they walk away.
4.01 | Password Rules | Minimum digits in master password | Force users to create a master password that includes at least this many numeric digits. Once enabled, users with a master password using too few digits are prompted to change their master password. Value: The required number of digits. |  |  |  | *Does not apply to Federated Login*
4.02 | Password Rules | Minimum lowercase in master password | Force users to create a master password that includes at least this many lowercase letters. Once enabled, users with a master password using too few lowercase letters are prompted to change their master password. Value: The required number of lowercase letters. |  |  |  | *Does not apply to Federated Login*
4.03 | Password Rules | Minimum uppercase in master password | Force users to create a master password that includes at least this many uppercase letters. Once enabled, users with a master password using too few uppercase letters are prompted to change their master password. Value: The required number of uppercase letters. |  |  |  | *Does not apply to Federated Login*
4.04 | Password Rules | Minimum special characters in master password | Force users to create a master password that includes at least this many special characters or symbols, such as !@,^. Once enabled, users with a master password using too few special characters are prompted to change their master password. Value: The required number of special characters. |  |  |  | *Does not apply to Federated Login*
4.05 | Password Rules | Require master password on site login | Force users to re-enter their master password upon login to a site from their vault. | Once this policy is enabled, LastPass will prompt the user for their master password at every site login. This results in no autofill behavior, all website logins are manual (the user must click the login button on the site). |  |  | *Does not apply to Federated Login*
4.06 | Password Rules | Require Password on Copy/View | Force users to re-enter their master password upon attempt to copy or view a password from their vault. |  |  |  | *Does not apply to Federated Login*
4.07 | Password Rules | Require master password change when reuse detected | Force users to change their master password upon detecting that it matches the password for any site in their vault. If an employee saves a site password to their vault that matches their master password, they are immediately logged out of LastPass and, upon next login, are forced to change their master password. | As a best practice we recommend enabling this policy to ensure master passwords are unique and not used as a site password. |  |  | *Does not apply to Federated Login*
5.01 | Account Restrictions | Prohibit Export | Prohibit users from exporting their account data. Advanced tip: To hide the export option in the client software, use the installer switch -dexp. Given that this is a client-side restriction, this policy cannot fully prevent exporting. The policy makes it more difficult for users to access the export option from the product interface. | As a best practice we recommend enabling this policy. If a user has a legitimate need to export it can be temporarily disabled, or they can be excluded to allow them to do an export.
5.02 | Account Restrictions | Prohibit Import | Prohibit users from importing their account data. Advanced tip: To hide the import option in the client software, use the installer switch -dimp.
5.03 | Account Restrictions | Prohibit Sharing | Prohibit users from sharing sites, notes, and other data. Advanced tip: To hide sharing options in the client software, use the installer switch -dsha.
5.04 | Account Restrictions | Prohibit Shared Folders Outside Enterprise | Prohibit users from sharing Shared Folders with anyone outside your Enterprise account except users at permitted domains. Value: To limit all outside sharing, enter 1. To allow access from certain domains, enter permitted domains separated by comma (example: aaa.com,bbb.com) | As a best practice if there is no use case for external password sharing, we recommend enabling this policy.
5.05 | Account Restrictions | Restrict sharing by domain | Only allow sharing from specified domains. Prohibit sharing from domains not listed below. Value: Enter permitted domains, separated by commas. For example: aaa.com,bbb.com
5.06 | Account Restrictions | Prohibit master password reversion | Do not allow users to revert to their previous master password within 60 days of the change. |  |  |  | *Does not apply to Federated Login*
5.07 | Account Restrictions | Disable Identities | Disable the Identities feature and remove it from the website and browser extensions. | Manage Identities is an older feature (accessed from your Vault > More options) used to create profiles, for example to manage Work and Home related sites. This feature is no longer a focus since Linking Personal accounts was introduced.
5.08 | Account Restrictions | Disable Secure Notes | Prohibit users from using the Secure Notes feature. Once enabled, existing notes remain available. Advanced tip: To disable the secure notes options in the client software, please see the 'DISABLENOTES' optional parameter argument of the LastPass Universal Installer, to hide the secure notes feature for the Firefox and Internet Explorer browser plugins.
5.09 | Account Restrictions | Don't show TOTP in vault | Prevent users from seeing time-based one-time passcodes (TOTP) in their LastPass vault.
5.1 | Account Restrictions | Disable Form Fillable Items | Disallow your users from using the following fillable items. In the 'value' field, enter the number of the fillable item to disable. You can separate multiple entries with coma. For example: 3,2 0 - All 1 - Notes 2 - Address 3 - Payment Card 4 - Bank Account 5 - Driver’s License 6 - Passport 7 - Social Security Number 8 - Insurance Policy 9 - Health Insurance 10 - Membership 11 - Wi-Fi Password 12 - Email Account 13 - Instant Messenger 14 - Database 15 - Server 16 - SSH Key 17 - Software License 18 - Custom Item | As a best practice you may consider disabling the personal related form fillable items. For example, enter values 5,7,,9 to remove the option to create entries related to Driver's License, Social Security and Health Insurance. It may be more appropriate for these entries to belong in a personal vault, not a business account.
5.11 | Account Restrictions | Disable Fingerprint Reader Authentication | Prohibit users from using Fingerprint Reader Authentication.
5.12 | Account Restrictions | Prohibit Bookmarklets | Prohibit users from installing Bookmarklets. | Bookmarklet is a special type of 'Favorite' or 'Bookmark' that can execute JavaScript on webpages, allowing users to fill data on browsers or devices where they normally wouldn't be able to install the LastPass browser extensions. This is not a commonly used feature. Accessed from your Vault > More options.
5.13 | Account Restrictions | Prohibit Master Password Hint | Prohibit users from saving a master password hint. |  |  |  | *Does not apply to Federated Login*
5.14 | Account Restrictions | Don't send email upon account deletion | Don't notify users via email when an administrator deletes their account.
5.15 | Account Restrictions | Prohibit Linked Personal Account | Prohibit users from linking their personal account to their Enterprise account.
5.16 | Account Restrictions | Prohibit update of personal account info | Prevent users from adding, updating, or deleting personal account data when their personal account is linked to your Enterprise account.
5.17 | Account Restrictions | Set default account for new sites | Force sites outside the specified domains to be saved to a user's linked personal account. Value: Enter each domain that should be saved to a user's work/Enterprise vault, separated by commas. For example: aaa.com,bbb.com.
5.18 | Account Restrictions | Save Personal Sites to Personal Vault | By linking their personal account to their work account, users gain access to both LastPass vaults with a single login to their enterprise account. When this policy is enabled, sites with a username matching the user's linked personal account are saved directly to the personal vault. Sites with any other username are saved to the work vault. | As a best practice we recommend enabling this policy. A personal LastPass account must be linked to the user’s business account in order for sites to auto-sort. Without this policy set, all logins will save to the work vault by default. When saving a site users can override the LastPass personal account designation by selecting 'Edit' if desired. When enabled, once a site is saved to their vault the user will not be able to move any sites that use their business account username (@company.com) from their company managed vault to their linked personal vault. Only sites with a username that doesn't match their company username can be moved to a linked personal account.
5.19 | Account Restrictions | Recommend or Require Linked Personal Account | When enabled you can Require or Recommend users to create a personal account linked to their Enterprise account. Users in your Enterprise with an existing personal account are required to link it to their Enterprise account. Users without a personal account are required to create one using their personal email address as their username. Value: Enter value of 1 to force or require a linked account; Enter value of 2 to recommend a linked account. | Best practice is to recommend users set up a personal linked account. If policy is not enabled users will still have option to 'Link Account' in their vault, unless linked accounts are prohibited.
5.2 | Account Restrictions | Restrict Enterprise API to Event Reporting | Prevent the LastPass Enterprise API from being used for anything other than reporting. When enabled, you can only call the Enterprise API with cmd=reporting. Any other endpoints will result in an unauthorized error. If your AD Sync gets broken after calling the Enterprise API, then you must generate a new provision hash for both AD Sync (using the latest LastPass AD Connector) and the Enterprise API.
5.21 | Account Restrictions | Hide Cloud Apps from end users | If you are not using LastPass SSO, prevent end users from accessing LastPass SSO features by removing the Cloud Apps menu item from their vault. | Best practice is to enable this policy if not using LastPass SSO.
5.22 | Account Restrictions | Disable Autofill | Prohibit users from automatically filling passwords on platforms other than mobile apps. This includes, for example, Chrome, Firefox, Safari and Edge on a PC or Mac. AutoFill remains available to users of the LastPass mobile app. This policy disables the option 'Automatically Fill Login Information' in LastPass Preferences.
6.01 | Administration | Don't send welcome email | When using automatic provisioning, don't send a welcome email to new users.
6.02 | Administration | Don't send email when adding users to shared folder | Don't notify users automatically by email when you add them to a shared folder.
6.03 | Administration | Don't send email upon account change | Don't notify users via email when an administrator changes their account email or master password.
6.04 | Administration | Don't send email upon master password reset | Don't notify users via email when an administrator resets their master password using the 'Permit super admins to reset master passwords' policy.
6.05 | Administration | Prevent Upgrade Prompts on Internet Explorer | If enabled, this policy will prevent the LastPass IE plugin from automatically upgrading. It will also prevent users from seeing prompts when IE upgrades are available. Click the 'enabled' box to enable this policy. | You will want to enable this policy If you are running on IE, as your systems are likely old enough that you want to control any and all updates to them. Also best practice for IT if you have a version control regime internally that tests all updates before allowing those updates to be sent out.
6.06 | Administration | Notify admins upon added/removed user | Send an email to the specified addresses upon user account creation or deletion, but not upon deactivation. This is useful when using automatic provisioning or our Active Directory client. Value: Enter email addresses separated by commas.
6.07 | Administration | Grant limited access to admin console | Grant users limited access to the admin console. First, click 'Edit Users' to add users. Second, under 'Notes', enter the level of access (1, 2, 3, or 4). 1 - Only allows the Reset Master Password function for users, but not full admins. 2 - Disable multifactor authentication for users + (1) 3 - Management of the Users page + (1 and 2) 4 - Management of the Users and Groups pages + (1, 2 and 3) Only values between 1-4 are accepted. Notes: *Once added here, you must add each user to the 'Permit super admins to reset master passwords' policy. *Adding a user to this policy prevents them from being added to custom Roles. *After adding a user to this policy, they will show as an Administrator on the Users page. | Enabling this policy will allow you to assign and admin limited Admin Console access to perform limited user management functions.
6.08 | Administration | Notify admins upon event | Notify admins about specified events for the selected user, users, or groups. login: When a user successfully logs in to their LastPass account failedlogin: When a user makes a failed attempt to log in to their LastPass account Separate multiple events by commas or spaces. Email notifications are sent to the selected user. However, you may optionally specify an alternate email address to send notifications to, distinct from the active user. To do so, specify the email address of the user account to send notifications for, followed by an equals '=' character, and then the email address that will receive the notifications. For example: failedlogin=elmer@mydomain.com
6.09 | Administration | Prevent User Status Emails to Shared Folder Admins | Disable automated emails to shared folder admins regarding change in user account status. | Consider enabling this policy to prevent email notifications from going to Shared folder admins when an employee is terminated or removed from the folder, before termination announcement. However, it is best practice to change shared passwords when someone leaves the organization, and the user status change email can remind shared folder admins to take action at that time.
6.1 | Administration | Restrict domain for LastPass username | Only allow users to use an email from an approved domain when creating a username for their LastPass account. No accounts can be created or updated using a username outside the approved domains. Value: Enter the allowed domains, separated by commas. For example: lastpass.com,xmarks.com | As a best practice we recommend enabling this policy and entering your approved domain values. When enabled this policy prevents a user from changing their company account username (email address) to a Gmail account or other non-AD username when creating their account.
6.11 | Administration | Prohibit account email change | Prohibit any email address change to a users account. | Prevents users and admins from changing LastPass account email addresses. As a best practice consider restricting domains allowed for LastPass usernames through the Restrict domain for LastPass username policy.
6.12 | Administration | Disable PasswordPing checks | Disable PasswordPing checks: -Daily checks for LastPass account emails -Security Challenge reports -Email notifications Learn more at https://blog.lastpass.com/2017/07/keeping-you-safe-in-a-world-full-of-breaches.html/ | Password Ping is a partner of ours that checks for email breaches during the Security Challenge.
6.13 | Administration | Log username in reporting | By activating this policy, you allow LastPass to store username data unencrypted and to provide that data to you in reports. This policy goes into effect upon next user login. Important: LastPass never stores username data unencrypted unless you activate this policy. EXAMPLE If a user logs in to the site 'alphabet' with URL https://abc.com/, then by default we display 'abc.com'. With this policy enabled, we display 'abc.com (alphabet)'. | As a best practice we recommend enabling this policy for more complete auditing logs. https://support.logmeininc.com/lastpass/help/generate-enterprise-reports-lp010040
6.14 | Administration | Log full URL in reporting | Show full URL (server + path, but no HTTP parameters) in reports rather than just the domain name of the site. This is often useful to distinguish which service is being accessed if many different resources are located on the same internal server. This policy goes into effect upon next user login. EXAMPLE If a user logs into https://def.abc.com/login.php?a=1, then by default we would display 'abc.com', but with this policy enabled we would display 'def.abc.com/login.php'. | As a best practice we recommend enabling this policy for more complete auditing logs. https://support.logmeininc.com/lastpass/help/generate-enterprise-reports-lp010040
6.15 | Administration | Log item name in reporting | Show name of site/note in reports. The name data (which is typically never sent to LastPass in unencrypted format) is sent by the client when reporting a login event and is shown in the admin reports. This policy goes into effect upon next user login. EXAMPLE If a user logs in to the site 'alphabet' with URL https://abc.com/, then by default we display 'abc.com'. With this policy enabled, we display 'abc.com (alphabet)'. Note: If all 3 polices are enabled, the output would look similar to the following: login.salesforce.com/ (john.smith@email.com) (Customer Support Salesforce login) from Support Logins Where: login.salesforce.com/is the Full URL john.smith@email.com is the username Customer Support Salesforce Login is the name of the item Support Logins is the name of the Shared Folder | As a best practice we recommend enabling this policy for more complete auditing logs. https://support.logmeininc.com/lastpass/help/generate-enterprise-reports-lp010040
6.16 | Administration | Notify admins upon creation of sharing key | Send an email to the specified addresses upon creation of user sharing keys. A user's sharing key is automatically created the first time they log in to the LastPass extension, or manually at LastPass.com on the Settings page. A user must have sharing keys to share or receive shared items.
7.01 | Multifactor | Prohibit multifactor disable via email | When enabled, prevent users from bypassing multifactor authentication via email notification. If this policy is set, the only way to disable second factor is through the admin console by an administrator. |  |  |  | *Does not apply to Federated Login*
7.02 | Multifactor | Require use of LastPass Authenticator | Require users to set up and use LastPass Authenticator as their second factor of authentication when logging in to LastPass. |  |  |  | *Does not apply to Federated Login*
7.03 | Multifactor | Require use of LastPass MFA | Require use of LastPass MFA as a second factor of authentication when logging in to LastPass. LastPass MFA is available as part of a LastPass Identity subscription. | The LastPass MFA app is separate from the LastPass Authenticator app. LastPass MFA app only pertains to LastPass MFA and LastPass Identity customers. |  |  | *Does not apply to Federated Login*
7.04 | Multifactor | Require use of YubiKey | Require users to set up and use YubiKey as their second factor of authentication when logging in to LastPass. Tip: Share this setup guide with your users: https://support.logmeininc.com/lastpass/help/yubikey-multifactor-authentication-lp030020 |  |  |  | *Does not apply to Federated Login*
7.05 | Multifactor | Require use of LastPass Sesame | Require users to set up and use LastPass Sesame as their second factor of authentication when logging in to LastPass. Tip: Share this setup guide with your users: https://support.logmeininc.com/lastpass/help/sesame-multifactor-authentication-lp030023 |  |  |  | *Does not apply to Federated Login*
7.06 | Multifactor | Require use of Google Authenticator | Require users to set up and use Google Authenticator as their second factor of authentication when logging in to LastPass. Tip: Share this setup guide with your users: https://support.logmeininc.com/lastpass/help/google-authenticator-lp030015 |  |  |  | *Does not apply to Federated Login*
7.07 | Multifactor | Require use of Microsoft Authenticator | Require users to set up and use Microsoft Authenticator as their second factor of authentication when logging in to LastPass. |  |  |  | *Does not apply to Federated Login*
7.08 | Multifactor | Require use of Toopher | Require users to set up and use Toopher as their second factor of authentication when logging in to LastPass. |  |  |  | *Does not apply to Federated Login*
7.09 | Multifactor | Require use of Duo Security | Require use of Duo Security as a second factor of authentication when logging into LastPass. You must enter your integration key, secret key, and API hostname in the boxes below. Duo Security must be configured by the user. To require Duo Security X days after the user account is created, enter a number in the value field below. | Go to Setting > Enterprise Options > Multifactor options to setup Duo keys: Duo Security integration key Duo Security secret key Duo Security API hostname |  |  | *Does not apply to Federated Login*
7.1 | Multifactor | Require use of Transakt | Require users to set up and use Transakt as their second factor of authentication when logging in to LastPass. |  |  |  | *Does not apply to Federated Login*
7.11 | Multifactor | Require use of Salesforce Authenticator | Require users to set up and use Salesforce Authenticator as their second factor of authentication when logging in to LastPass. |  |  |  | *Does not apply to Federated Login*
7.12 | Multifactor | Require use of any MFA (multifactor) option | Require users to enable a multifactor authentication option. To define the list of valid multifactor options available to users, go to Advanced Options > Enterprise Options in the Admin Console. Currently available options: LastPass Authenticator, YubiKey, LastPass Sesame, Google Authenticator, Toopher, Duo Security, SecureAuth, Transakt, Salesforce Authenticator, RSA SecurID, and Symantec VIP. Note: Fingerprint and Grid cannot be managed through require use policy. | As a best practice we recommend protecting vaults with 2-factor authentication. Use this policy to offer multiple authenticator options, or select one of our other multifactor policies to require a specific authenticator. This policy can be turned on after rollout but we recommend testing prior to rollout. Communication/process awareness is important when implementing. |  |  | *Does not apply to Federated Login*
7.13 | Multifactor | Allow users to skip MFA at trusted locations | Allow users to trust computers and bypass multifactor authentication when accessing LastPass from an approved location (such as your office), based on IP address. Value: Enter each allowed IP address or partial IP address, separated by white space. For example: 71.126.154. 128.8. 120.0.0.1 This allows any user located at 71.126.154.*, 128.8.*.* and 120.0.0.1 to trust their device and skip MFA. To disable trust altogether, enter 'none'. This is not retroactive. Computers previously trusted remain trusted after the policy is enabled. |  |  |  | *Does not apply to Federated Login*
7.14 | Multifactor | Prohibit offline access for TOTP MFA | Prevent users with Google Authenticator as their MFA option from gaining offline access to their account. This ensures that the local cache (or a time-based one-time password) can't be accessed without a second factor. |  |  |  | *Does not apply to Federated Login*
7.15 | Multifactor | Set code validity interval for Google Authenticator | Set the number of minutes for which codes generated by Google Authenticator remain valid for entry to LastPass. This helps resolve issues with clock drift on user devices. By default, LastPass considers Google Authenticator codes valid up to 4 minutes in the past and 4 minutes in the future. Value: Set a number between 1-5 (minutes). |  |  |  | *Does not apply to Federated Login*
7.16 | Multifactor | Prohibit multiple YubiKeys | Prohibit users from setting up more than one YubiKey for their account. Otherwise, they are allowed up to five YubiKeys. |  |  |  | *Does not apply to Federated Login*
7.17 | Multifactor | Use local-part of email as Duo Security username | Use only the local-part (username portion before @) of a user's email address to create their Duo Security username. For example: If the user's email address is 'local-part@domain.com', their Duo Security username is 'local-part'. |  |  |  | *Does not apply to Federated Login*
7.18 | Multifactor | Require MFA for admin console | Require logged in admins to complete MFA when accessing the admin console after this many minutes of inactivity. Value: Set a number of inactivity minutes before users accessing the enterprise console will be required to re-authenticate via multifactor after not using. |  |  |  | *Does not apply to Federated Login*
7.19 | Multifactor | Require action for out-of-band MFA | Prevent out-of-band MFA services (Toopher, Duo Security, Transakt) from creating push notifications. |  |  |  | *Does not apply to Federated Login*
7.2 | Multifactor | Use Duo Web SDK when possible | When possible, use the Duo Web SDK instead of the LastPass Duo Security GUI. Some LastPass features are disabled, such as automatic push notification. |  |  |  | *Does not apply to Federated Login*
7.21 | Multifactor | Skip MFA at trusted locations | Users logging in from listed addresses are not prompted for multifactor authentication. Value: Enter each allowed IP address or partial IP address, separated by white space. For example: 71.126.154. 128.8. 120.0.0.1 This allows login without multifactor from any address in 71.126.154.*, 128.8.*.* and 120.0.0.1. We also support CIDR Notation. For example: 61.12.56.0/24 allows any address in 61.12.56.* to log in. | The Skip MFA at trusted locations policy pertains to LastPass MFA and LastPass Identity customers. |  |  | *Does not apply to Federated Login*
8.01 | Other | Force logoff from background | Force logoff after the app is in the background for the specified number of minutes. | By default, the LastPass mobile app continues to run in the background until the operating system kills it or until the device is restarted. Enabling this policy ensures the user's session will end so that the user will be prompted to authenticate again after the app has been in the background for a designated period of time.
8.02 | Other | Prohibit 'Remember master password' on mobile | Prevent users from remembering their master password to the app on their mobile. | Remembering the password weakens the security for that user, we recommend enabling this policy as a best practice.
8.03 | Other | Override mobile lock option | Force users to log in or re-enter their PIN to unlock the app after the specified period of app inactivity. Supported on LastPass for iOS 4.1.8 or higher and LastPass for Android 4.2.290 or higher. Value: Enter value for allowed period of inactivity, as follows: 0 - Immediately 1 - 1 minute 2 - 3 minutes 3 - 5 minutes 4 - 15 minutes 5 - 1 hour 6 - 8 hours 7 - 24 hours 8 - Never | As a best practice we recommend enabling this policy. Enabling the mobile lock option override will ensure users are locking the app in the background.
8.04 | Other | Password expiration notification | Report on password expiration status for each employee. List domains to monitor, including the expiration period per domain (90 days if not otherwise specified). An asterisk indicates all domains. To send a report of expired accounts to an admin, include email addresses. To send the email a certain number of days after expiration, add a colon and a number. For example: domain.com:83, domain2.net:173, *:53, admin@domain.com:7 Users are notified for passwords 53 days old for all domains, 83 days old for domain.com, 173 days old for domain2.net, and admin@domain.com is alerted 7 days after user notification. | Enabling this policy can notify users and/or admins when site passwords are over a certain age. LastPass cannot force you to update stored passwords at specified intervals, but if you want to notify people to change certain passwords at specified intervals using this policy will help you to enforce that.

## Communication Plan
LastPass Communication Action Plan
Phase | Tasks | Details | Owner | Date(s) | Status | Notes
Pre-Launch Phase Create awareness of LastPass | 1. Build awareness of LastPass. | Hang posters or distribute flyers around the office. Post about LastPass on your intranet, digital signage, or employee blog. Build awareness of how LastPass will be easy, convenient, and save employees time.
| 2. Train the trainers. | Conduct product review training for admins, helpdesk, or other employees that will need to support LastPass usage and adoption. Include Admin and End-User trainings.
| 3. Develop communication materials. | Create an activation and installation guide to help users self-guide through the account creation process. Create internal repository of resources and support information for FAQs (SharePoint, Slack or Teams channel)
| 4. Notify employees by email. | Send at least one email (including the executive sponsor email) to let users know you'll be providing a password manager that will save them time and make them more secure. Share your company's expectation for usage and include where to find more information.
Phase One: Day 1-14 Onboard pilot group | 1. Identify and roll out to select groups. | We recommend groups such as IT, Legal, Marketing and HR - a cross-section of employees and technical experience. Ensure all policies are set up correctly (see the Deployment Plan), instructions are clear, and these groups are properly trained. This is your internal trial group. By rolling out to these groups first, it will get the attention of the other groups, and in most cases this will build some anticipation.
| 2. Conduct pilot end-user training. | Present an overview of password management and the benefits of LastPass, with an interactive demo of how LastPass works. If possible, let employees use their laptops to set up and start using their accounts.
| 3. Weekly Calls with stakeholders. | Review usage, collect feedback and suggestions, and review open items.
| 4. Phase 1 wrap up report. | Was phase 1 successful? How did it meet success criteria? What worked? What didn't work? What could be done better? Share your findings with you LastPass CSM.
Phase Two: Day 15-30 Onboard the entire organization | 1. Roll out LastPass to the rest of the organization. | Send invites to all users, automating through your user directory where applicable.
| 2. Notify employees by email. | Send email to all end-users that includes training materials.
| 3. Schedule end-user training and workshops. | Whether virtual or on-site, host trainings that provide an overview of password management and how LastPass works. Record the trainings for reference.
| 4. Weekly Calls with stakeholders. | Review usage, collect feedback and suggestions, and review open items.
| 5. After 2 weeks send reinvite to users who have not activated their account. | From the admin dashboard, review inactive users and send an email. Also identify employees with low usage and re-share training materials.
| 6. Kick off a challenge. | Communicate the competition, activity, and/or reward that you will use to drive adoption.
| 7. Phase 2 wrap up report. | Was phase 2 successful? How did it meet success criteria? What worked? What didn't work? What could be done better? Share your findings with you LastPass CSM.
Phase Three: Day 30-60 Reinvite and continue training | 1. Send email to inactive users. | Notify any employees that have failed to activate their accounts. Understand hurdles to activation and work to address them.
| 2. Reinvite non-active users. | From the admin dashboard, review inactive users and send an email. Also identify employees with low usage and re-share training materials.
| 3. Reward the top X% of users with best usage. | Identify your top users and reward them (gift cards, t-shirts, etc.). If you conducted a challenge, announce the winners.
| 4. Bi-Weekly Calls w/stakeholders. | Review usage, collect feedback and suggestions, review open items. Are we on track with success metrics?
| 5. Create a user success story. | Who are your top 10 users? Why are they so successful? Create a story and share it.
| 6. End User Surveys. | Why are you not using it? What is working? What is not working? Do you know the value of LastPass?
| 7. Schedule more trainings and workshops as needed. | Schedule follow-up trainings to cover core and advanced LastPass features. Help employees activate their account and start seeing the benefit of saving, filling, generating and sharing passwords with LastPass.
| 8. Phase 3 wrap up report. | Was phase 3 successful? How did it meet success criteria? What worked? What didn't work? What could be done better? Share your findings with you LastPass CSM.
Phase Four: Day 60-90 Ongoing maintenance | 1. Send email to users who have not used LastPass. | From the admin dashboard, review inactive users and send an email. Also identify employees with low usage and re-share training materials.
| 2. Monthly Calls with stakeholders. | Review usage, collect feedback and suggestions, review open items. Are we on track with success metrics?
| 3. Schedule additional trainings and workshops as-needed. | Schedule follow-up trainings to cover core and advanced LastPass features. Help employees activate their account and start seeing the benefit of saving, filling, generating and sharing passwords with LastPass.
| 4. Phase 4 wrap up report | Was phase 4 successful? How did it meet success criteria? What worked? What didn't work? What could be done better? Share your findings with you LastPass CSM.
Phase Five: Day 90+ Lifecycle maintenance | 1. Run weekly/monthly reports to measure adoption, usage and security. | From the admin dashboard, review User Activity reports and Security reports to determine your inactive users and security risks. You can also use automated Email Notifications from LastPass to identify employees at risk.
| 2. Send emails to users who have not used LastPass. | Perform active outreach to users who are not actively using LastPass and investigate roadblocks to adoption. Best practice is reaching out to at risk employees with personally directed emails from the LastPass Admin.
| 3. Quarterly calls with stakeholders. | Review usage, collect feedback and suggestions, review open items. Are we on track with success metrics?
| 4. Schedule additional trainings and workshops as-needed to target security ricks and poor usage. | Schedule follow-up trainings to cover core and advanced LastPass features. Help employees activate their account and start seeing the benefit of saving, filling, generating and sharing passwords with LastPass.

## Training Plan
LastPass Training Action Plan
Phase | Action Item | Details | Owner | Date(s) | Status | Notes
Pre-Training Considerations | 1. Review LastPass features | Will users have their devices with them in the room (i.e. laptops, mobile phones)?
| 2. Confirm Admin Console and Policies Settings Configured | Will users already have the LastPass extension installed on their browsers? If not, do they have the proper permissions for download so that we can help them install onsite?
Will users be creating Master passwords or using Federated Active Directory logins?
Will users already have been invited to create their account so they can follow along and ask questions during the training?
Are you mandating or encouraging the use of multi-factor authentication? If so, which option(s)?
Are you mandating or encouraging the use of a personal linked LastPass account? If not, are you prohibiting the use of a personal linked account?
Are you allowing Sharing and/or Shared Folders?
Are you allowing users to access their account from mobile devices?
Are you implementing SAML Single Sign-On with LastPass?
Training Development | 1. Create custom training materials.
| 2. Leverage existing Live, Recorded and Self-Paced Training materials. | Admin Toolkit, End User Toolkit, Embark training portal -Tutorial videos -FAQs -Support resources -Recorded trainings -Handouts, flyers, and more
| 3. Determine a central repository for training materials. | Determine your primary communication channel(s) and storage for documentation, recordings, and other materials. Intranet? OneDrive?
| 4. Incorporate materials in all email communications. | Remind employees where they can find handouts and support resources to help them get started with LastPass.
Training Agenda | 1. What is LastPass? | > Password Manager > Ability to securely store passwords > Secure password generating tool
| 2. Why use LastPass? | > Benefits to the user and the employer > Security for company and personal (Linked account) passwords > Makes your password life simpler because you don't have to remember passwords anymore
| 3. Introduction to LastPass basics | > Downloading LastPass > How LastPass works: local/offline, everywhere access, the security model > Creating an account and a strong master passphrase > Setting up account Manage Account settings > Linking a personal account > Storing sites in the business account > Storing sites in the linked personal account > Registering for new sites > Hands-free login and multiple accounts on the same domain > Generating passwords > Updating passwords
| 4. Advanced LastPass features | > Multi-factor authentication > Shared Folders > Creating and using secure notes > Creating and using form fill profiles > The LastPass security challenge > Mobile access for iOS and Android > Advanced settings
Live Training Preparation | 1. Send the welcome email 24 hours prior to training
2. If users have been invited before, please reinvite users from the Admin Console: From Dashboard > Reinvite All From Users > Select User > Select ellipsis > select action "Reinvite user"
| 3. Where is training? | Onsite, in person, or via virtually hosted meeting.
| 4. Who is the training for? | Company-wide, targeted groups, select teams for phased roll-out?
| 5. When is training taking place? | Lunch and learns? Record the live trainings to share later. Post recorded trainings where employees can find them, whether they weren't able to attend or just need a refresh of the material.

## Adoption Best Practices
LastPass Adoption Best Practices
| Action Item | Description | Owner | Dates | Status | Resources
Top Adoption Drivers | Assign an Executive Sponsor | We recommend selecting a C or V level Executive to champion LastPass internally and receive regular reports of progress on the rollout.
| Make LastPass mandatory | Consider creating a company policy that all employees are mandated to use LastPass. Deploy user training portal to track employee progress. Monitor employee usage in Admin Console through Email Notifications and Security Reports.
| Linked Personal accounts | Driving adoption comes from within your organization. Show users the value of securing their work and personal lives with Linked Personal accounts. When you link your personal LastPass account with your company account, you can keep your Vault entries all in one place while both accounts remain separate. Your personal account will continue to remain private (your company admin is never able to view your personal account data), and if you ever leave the company, your personal account data remains active and accessible to you. Additionally, login events for your personal account will never be logged in admin reporting. |  |  |  | Support Article: Link your personal account
| Integrate with your user directory | By integrating with your existing directory, every employee can be automatically onboarded to LastPass when they join the company, as well as off-boarded when they leave. You'll simplify day-to-day management for admins while spreading usage in the organization. |  |  |  | Support Article: Directory Integration methods for Automated Provisioning
| Federate Users with your active directory | Federation integrates an Identity Provider (Active Directory, Azure Active Directory, or Okta) with a service provider (in this case, LastPass) so that when a user is authenticated into the Identity Provider, they will also be logged into the service provider. In terms of LastPass, this means the need for using a separate Master Password is eliminated for users with federated login. |  |  |  | Support Article: Limitations for Federated Users
| Configure Single-Sign On Cloud Apps | LastPass Single Sign-on allows you to utilize your LastPass account as the central point of authentication for a various domains and associated services. LastPass SSO is powered by SAML 2.0, which allows your employees to access their favorite services simply by being logged in to LastPass. Once logged in to LastPass, your users can navigate to the service’s URL and bypass the login screen altogether. |  |  |  | Support Site: Single-Sign-On | SSO Application Catalog
| Hardwire LastPass using Push sites | Consider pre-loading user vaults for new hires with passwords they need to do their work. When they see that the vault is set up for them and LastPass starts filling their passwords automatically, they’ll instantly see the value of the service. |  |  |  | Support Article: Push Sites to LastPass Users
| Formalize a communication strategy | Develop a plan for raising awareness of LastPass and training employees to use the tool. See Communication Plan tab and Communication Strategy Best Practices below.
| Have an internal repository for user resources | Consider taking a few of the most valuable support articles and load them into an internal directory for your users. Uses are more likely to visit an internal directory or Intranet to find out more information or troubleshoot than a third party vendors website. Ask your CSM for an example of an organization who has done this successfully.
| Invest in employee training | Educate employees on why a password management tool is necessary and the importance of cybersecurity. Highlight how the employee will benefit. LastPass will protect the individual as an employee and a consumer. Use metrics and statistics to communicate the value (81% of breaches are password-related. Average cost of breach is nearly $4 million.).
| Go mobile | 56% of web traffic comes from a mobile device. The LastPass mobile app is not only easy to use, but will increase adoption. Encourage mobile use and train on the mobile product experience. |  |  |  | Support Article: LastPass for Android | Support Article: LastPass for IOS
| Create and report on success metrics | LastPass Reports feature offers admins an audit trail of User and Admin Activity that be exported and shared with key stakeholders as needed. How can you measure success in LastPass? What metrics can LastPass help you track? What is important to you? |  |  |  | Support Article: Generate Reports
| Add LastPass to your Corporate Policies | Before deploying LastPass, you may want to update your internal IT policies and/or employee guidebook to specifically reference LastPass. Doing so will help set expectations for why employees should use LastPass, and best practices for using it. |  |  |  | Support Article: Adding LastPass to your Corporate Policies
| Identify internal champions | Identify internal advocates for your LastPass deployment, whether people who are already using LastPass or are excited to use it. Reward them (t-shirts, gift cards, public recognition, etc.) and point others to them as a resource for people who have questions about LastPass.
| Make it fun! | Launch a competition or activity, and announce a prize on best usage of LastPass. For example: The first team to achieve 100% adoption of LastPass wins a prize.
| Commit to regular check in calls with your LastPass Admin Team | Attending regular LastPass meetings are critical to successful adoption. We will keep you updated on usage, best practices, and make recommendations.
Employee Training Best Practices | Schedule and record live trainings. | Where and when? Onsite, or via GoToMeeting? Lunch and learns? Record the live trainings to share later. Post recorded trainings where employees can find them, whether they weren't able to attend or just need a refresh of the material.
| Leverage existing LastPass materials. | Admin Toolkit, End User Toolkit, Embark training portal -Tutorial videos -FAQs -Support resources -Recorded trainings -Handouts, flyers, and more |  |  |  | Embark training portal | Series of LastPass 101 short videos
| Determine a central repository for materials. | Determine your primary communication channel(s) and storage for documentation, recordings, and other materials. Intranet? OneDrive?
| Incorporate materials in all email communications. | Remind employees where they can find handouts and support resources to help them get started with LastPass.
Communication Strategy Best Practices | Customize the LastPass welcome email. | LastPass generates a default welcome email for users added to your organization's LastPass account. Customize the content from the admin dashboard (in the Users tab, click Add User, Edit Preferences for the email, and select the Custom email option). |  |  |  | Welcome Email Template | Support Article: Email Templates for Inviting New LastPass Users
| C-level executive announcement email. | After determining your executive sponsor, work with them to craft an email expressing excitement over LastPass, why it's an important initiative, and the benefits employees will receive by using the service. |  |  |  | Support Article: Executive Welcome to LastPass Email Template
| Adapt training to your employees. | How do you train employees on other products? What works for your users? Hands-on? In-person training? OnDemand Videos? User Guides?
| Spread awareness with visual materials. | Use Posters, Flyers, Digital Signage and other visuals to raise awareness and drive interest. |  |  |  | LastPass Admin Toolkit -- Awareness and Education resources
| Promote mobile usage. | Unless you are disallowing mobile access via policies, make sure users are aware of the benefits of taking LastPass with them on all of their devices, so they have their passwords no matter where they're working. |  |  |  | Support Article: LastPass for Android | Support Article: LastPass for IOS
| Promote personal linked accounts. | Unless you are disallowing linked personal accounts via policies, make sure users are aware of the benefits of Linked Personal accounts and keeping their work and personal lives secure and separate. If they ever leave the company, their personal data remains active and still accessible only to them.
| Survey your user end-users. | Survey your end-users after the implementation and on a TBD schedule after that so you can gage user's satisfaction and roadblocks to use to learn more about how users are or aren't using the tool. |  |  |  | Sample Survey Questions tab in this worksheet

## Security Risk Usage Monitoring
LastPass Security Dashboard! Review and share the following support articles with users to help increase their security score:
What is the security score in my Security Dashboard?
How do I use the Security Dashboard?
How do I change at-risk passwords in my LastPass Vault?
What is dark web monitoring?
Security Dashboard and Dark Web Monitoring - Admin FAQs
Learn more about Email Notifications for LastPass | https://support.logmeininc.com/lastpass/help/manage-email-notifications-for-lastpass-enterprise-lp010073
Admin Console > Advanced > Email Notifications >> LastPass admins can add and manage email notifications to keep apprised of critical user statuses, including account activation, lack of best practices being used (warranting additional education or training), and much more.
Notification Name | Description
Invitation not accepted | Users who have not accepted an invitation to join your LastPass business account within X hours of being invited. If manually invited, users need to click on the email invitation link to associate their existing LastPass account to your company's LastPass business account.
Account not activated | Users who have not activated their LastPass business account within X hours of being invited.
No sharing key | Users who do not have a sharing key. Users must login once using a LastPass plugin to generate a sharing key before you can share items with them.
Inactive | Users who have not logged in for more than X days.
Number of sites | Users who have less than X sites in their vault. Can set a minimum number expectation to monitor.
No Linked Account | Users who have not associated a personal LastPass account with their business account.
Weak master password | Users who have a master password strength of less than X percent. Weak master passwords are determined by assessing users security score.
Reused master password | Users who entered their master password on another site in the last X days and have since not changed their master password.
Weak security challenge | Users who have a security challenge score of less than X percent.
Weak passwords sites | Users who have more than X sites that have weak passwords.
Average password strength | Users whose average password strength is less than X percent.
Duplicate passwords | Users who have more than X duplicate passwords. Monitors the number of passwords being reused.
Duplicate password sites | Users who have more than X sites with duplicate passwords. Monitors how many sites are using a duplicate password.
Blank passwords | Users who have more than X sites with blank passwords.
Low number of entries | Users who have less than X sites, secure notes, and Fill Form profiles in their vault.
Low number of secure notes | Users who have less than X secure notes in their vault.
Low number of Fill Forms profiles | Users who have less than X Fill Form profiles in their vault.
Security Report | https://support.logmeininc.com/lastpass/help/generate-enterprise-reports-lp010040
Admin Console > Reporting >> General Reports feature offers admins an audit trail of User and Admin Activity that be exported and shared with key stakeholders as needed. Additionally the Security report assesses the following risks:
Risk name | Users affected ¦ % of x users
Reused Master Passwords
Weak Master Passwords
Invited Users That Haven't Activated
Weak Security Challenge Scores
Average Strength of All Passwords
Invitation not accepted
No sharing key
Inactive in last 7 days
No linked account
More than 5 weak passwords
More than 3 duplicate passwords saved in their vault*
More than 3 sites with duplicate passwords*
More than 3 blank passwords
Security report FAQ:
*Since LastPass does not store or save passwords, duplicate passwords are determined and evaluated by assessing the encrypted hash
Compliance, Risks, and Security Resources:
Technical Whitepaper
LastPass Compliance - What You Need to Know
LastPass Security
How is LastPass Safe?
Where is my LastPass Data stored?
LogMeIn Trust & Privacy Center

## Resources
Administrator Resources
Welcome to LastPass Video (3 minutes) | https://mfa-support.lastpass.com/
Official LastPass Help Center >> Type your question | https://support.logmeininc.com/lastpass/
Admin Toolkit - Evaluation, Implementation, Awareness & Education | https://support.logmeininc.com/lastpass/help/use-the-lastpass-enterprise-admin-toolkit-lp010027
Quick Helpdesk Guide for LastPass Enterprise Admins | https://assets.cdngetgo.com/4e/97/3fc5c80943789edacaefefb30e1c/lastpass-ent-user-helpdesk-guide.pdf
Security Topics | https://www.lastpass.com/enterprise/security
>> Security Overview Flyer | https://assets.cdngetgo.com/69/c0/2cef992e48eeba015c85312f16ce/lastpass-encryption.pdf
>> Technical Whitepaper | https://assets.cdngetgo.com/60/be/323790b344bf8e631ecb033e4cad/lastpass-technical-whitepaper.pdf
Access the Enterprise Admin Console | https://support.logmeininc.com/lastpass/help/access-the-admin-console-lp010019
How to Add Enterprise Users | https://support.logmeininc.com/lastpass/help/how-to-add-enterprise-users-lp010044
>> Adding LastPass Users Manually | https://support.logmeininc.com/lastpass/help/manually-add-enterprise-users-lp010045
>> Use Directory Integrations for Automated Provisioning | https://support.logmeininc.com/lastpass/help/use-directory-integration-for-automated-provisioning-lp010046
>> LastPass Active Directory Connector | https://support.logmeininc.com/lastpass/help/set-up-the-lastpass-active-directory-connector-lp010057
>> Federated Login Experiences | https://support.logmeininc.com/lastpass/help/federated-login-experience-for-lastpass-enterprise-users-lp010056
View and Manage Enterprise User Settings | https://support.logmeininc.com/lastpass/help/view-and-manage-enterprise-user-settings-lp010048
Setup Single Sign-On (SSO) | https://support.logmeininc.com/lastpass/help/set-up-single-sign-on-for-lastpass-lp010079
Push Sites | https://support.logmeininc.com/lastpass/help/push-sites-to-users-lp010077
LastPass Enterprise Installing Software | https://support.logmeininc.com/lastpass/help/install-lastpass-software-using-the-admin-console-lp010069
Register for Live Admin and End-User Training Webinars | http://link.lastpass.com/EmbAdmCSMEmails | http://link.lastpass.com/EmbUserCSMEmails
Find Posters and Training Links > in Toolkit Under Awareness & Education | https://support.logmeininc.com/lastpass/help/use-the-lastpass-enterprise-admin-toolkit-lp010027
Understand How Super Admin Password Reset Policy works | https://support.logmeininc.com/lastpass/help/reset-a-users-master-password-super-admin-lp010038
User Resources
Welcome to LastPass Video (3 minutes) | https://www.youtube.com/watch?v=oa9apKp_mHs&list=PLsXN_jRonzyctRhVdPUKGurKUArMEWcIM&index=2
Extended Getting Started--LastPass 101 (16 minutes) | https://support.logmeininc.com/lastpass/help/video-end-user-training-16-14-1309725811
Getting Started as an Enterprise User | https://support.logmeininc.com/lastpass/help/get-started-as-a-lastpass-enterprise-user-lp010051
End-User Instructional Setup Flyer > 1,2,3 - Go! Flyer | https://support.logmeininc.com/lastpass/downloaddocument/lastpass-getting-started-flyer-lpd00007
End-User LastPass Made Easy Reference Flyer | https://support.logmeininc.com/lastpass/downloaddocument/end-user-desk-reference-guide-lpd00013
How do I use LastPass on my Mobile Device | https://support.logmeininc.com/lastpass/help/how-do-i-use-lastpass-on-my-mobile-device
LastPass for iOS | https://support.logmeininc.com/lastpass/help/lastpass-for-ios-lp060002
LastPass for Android | https://support.logmeininc.com/lastpass/help/lastpass-for-android-lp060001
Register for Live User Training Webinar | http://link.lastpass.com/EmbUserCSMEmails
Downloading and Installing LastPass for Users | https://support.logmeininc.com/lastpass/help/download-and-install-lastpass-lp010007
Manage Browser Extension Preferences (does not override enterprise policy) | https://support.logmeininc.com/lastpass/help/manage-browser-extension-preferences-lp010009
Manage Account Settings | https://support.logmeininc.com/lastpass/help/manage-account-settings-lp010017
Manage LastPass Enterprise Shared Folders (Users) | https://support.logmeininc.com/lastpass/help/manage-lastpass-enterprise-shared-folders-users-lp010053
Manage Your Vault | https://support.logmeininc.com/lastpass/help/manage-your-vault-lp010015
How do I manage my site passwords? | https://support.logmeininc.com/lastpass/help/how-do-i-manage-my-site-passwords-lp010115
Require a Password Re-Prompt | https://support.logmeininc.com/lastpass/help/require-a-password-re-prompt-lp020009
Set Up Automatic Logins | https://support.logmeininc.com/lastpass/help/set-up-automatic-logins-lp020008
Disable Autofill for Sites | https://support.logmeininc.com/lastpass/help/disable-autofill-for-sites-lp020004
Use the Security Challenge | https://support.logmeininc.com/lastpass/help/use-the-security-challenge-lp030011
Training Resources
End User Tool kit | https://support.logmeininc.com/lastpass/help/lastpass-end-user-toolkit
End User Training Video | https://www.youtube.com/watch?v=oa9apKp_mHs&list=PLsXN_jRonzyctRhVdPUKGurKUArMEWcIM&index=2 | https://support.logmeininc.com/lastpass/help/video-enterprise-user-demo-14-52-1309856441
All Training Videos | https://www.youtube.com/channel/UCFLeKmbS3mmvGjXvZ5hnfKw
LastPass Videos in other languages
Spanish | https://www.youtube.com/watch?v=BUavGENCSHk&list=PLsXN_jRonzydkVHGrmLfTgl5FPPf5GXsM
French | https://www.youtube.com/watch?v=aNrDCiYdews&list=PLsXN_jRonzycvvw9W6kTi_HuGIoqvoLik
German | https://www.youtube.com/watch?v=6hrxcoQsTwA&list=PLsXN_jRonzyf7RJyZhCDF6hRUUDBcm3ta

## Sample Survey Questions
Sample End-User Roadblock Discovery Survey Questions
1. Are you familiar with LastPass?
Yes/No
2. Did you know there was a company LastPass account assigned to you? Or Did you know your company has a license available for you?
Yes/No
3. Are you actively using LastPass?
Yes/No
4. If you are not using LastPass, please select the reason why?
1) I didn’t know it was available / No one told me to use it
2) I never received training on how to use the tool
3) I ran into issues during set up
4) I don’t want to
5) Other __________
5. “LastPass is an easy tool designed to securely remember all of your passwords for you to increase productivity and decrease needing to reset passwords”. Based on that description of the tool, is LastPass a tool you would want to use?
Yes/No
6. If LastPass could be used to remember all of your work passwords, as well as at home with all of your personal accounts (Gmail, Facebook, bank accounts, etc.) all while never sharing information with your employer, would that increase your likelihood to use the tool?
Yes/No
Sample post-deployment survey questions
1. How easy was it for you to create your account and get started with LastPass?
Very Easy
Easy
Could have been easier (enter explanation here):
2. Tell us about your biggest hurdle with setting up or using your LastPass Account?
3. On a scale of 1-10, with 10 being the highest, Please rate LastPass's ease of use with other software and web apps you have used:
4. What value do you see using LastPass? (Check all that Applies)
The ability to generate and remember long, extremely complex Passwords?
Knowing that your data is encrypted with military and bank level encryption?
Only having to remember one password moving forward?
Other (Enter here):
5. Please rate your level of overall satisfaction with LastPass:
Very Satisfied
Satisfied
Somewhat Satisfied
Neutral
Somewhat Dissatisfied
Dissatisfied
Very Dissatisfied
6. What LastPass features are you most excited to start using? (Check all that Applies)
Storing Payment Cards, Bank Accounts, Wi-Fi Passwords and Addresses
Auditing my accounts using the LastPass Security Challenge
Changing any weak, reused, old or compromised passwords?
Using LastPass on my mobile device
Other (Enter here):
7. What feature would you like to see made available in the future?
8. Have you downloaded LastPass on your Mobile App?
Yes
No
I did not know LastPass had a mobile app
9. Do you have a linked personal LastPass account?
Yes
No
I did not know I could link a personal account to my LastPass business account
10. What type of additional LastPass training resources do you require in the future?
1:1 Training
Training videos work best for me
Face to Face Group Training
Interactive OnDemand Training
Vertical Group Training
I do not need additional training
11. Do you have any additional Questions or Feedback regarding LastPass?

## Dashboard
Insert screenshots of admin dashboard metrics to measure milestones and improvements during implementation and adoption